## Resource Pool Database
Location | Area | Manager | Associate
SlpP/TlP | PPS | Carreira Leandro (M/PPS-CC-NA) | Daniela Garcia Hernandez
Dario Andres Gonzalez Martinez
Amaury Martinez Garcia
Ray Edgardo Martinez Vargas
Ricardo Jose Vazquez Morales
Lucero Villegas Toranzo
SlpP | ENG | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez
Alejandro Antonio Lara Hernandez
Arnulfo Mauricio Serrano Alvarado
Julio Cesar Vera Vazquez
TlP |  |  | Gabriel Cruz Guzman
Alberto Levi Rossano Ruiz
SlpP | ENG | Gonzalez Loredo Jose Angel (PS-CC/ENG1-MX) | Diana Gabriela Cervantes Marin
Jose Daniel Garcia Larios
Rodolfo Lopez Halun
Carlos Alberto Monroy Medellin
Andres Navarro Chevaile
TlP |  |  | Carlos Omar Heredia Morales
Alejandro Ceballos Sanchez
Eric Maximiliano Marmolejo Ortiz
Edgar Dario Narciso Jordan
SlpP | QMM | De Souza Eduardo Henrique (PS/QMM-MSE3-SlpP) | Mauricio Anzures Enriquez
Alejandra Diaz Villela
Enny Paula Escobar Ruiz
Karen Linan Gomez
Eli Israel Mendez Lopez
Liliana Jaqueline Ramirez Quintanar
Juan Carlos Salas Sanchez
Karina Salazar Fuentes
TlP | QMM | Medina Gonzalez Fernando (EM/QMM4-Tl) | Rosario Gabriela Caltzonzin Mercado
Emerson Flores Chavez
Karla Fernanda Lechuga Gonzalez
Jesus Alejandro Ruiz Gonzalez
Alejandra Velazquez Nava
SlpP | LOD | Ovalle Juarez Aldo Cesar (SlpP/LOM SlpP/LOD1.1) | Jaime Alberto Casas Aleman Martinez
Jesus Estrada Vazquez
Luis Angel Fernandez Zapata
SlpP | LOP | Mueller Robin (SlpP/LOP2) | Pedro Alejandro Campos Martinez
Monserrat Canseco Roman
Maria Sandra Carranco Martinez
Evelyn Cerda Cerda
Harumi Anai Flores Cano
Pamela Garcia Arvizu
Jose Luis Jaramillo Merida
Ma. Elena Pruneda Castillo
Laura Isabel Torres Blanco
Carolina Valtierra Zavala
Carlos Eduardo Zavala Garcia
TlP | LOP5 | Albarran Aguirre Anayeli (TlP/LOP11) | Arturo Ivan Flores Maccise
Maria Guadalupe Hernandez Bejarano
Ana Karen Mejia Cayetano
Elsa Irma Mejia Estevez
Celia Villalobos Camacho
TLP | LOP4 | Lopez Munoz Alma Isabel (TlP/LOP4) | Natalia Gabriela Enriquez Valdez
Fabiola Hernandez Castillo
Paulina Hernandez Chavez
Pedro Arturo Lopez Martinez
Jaime Omar Marceleno Leija
Lisette Alejandra Pureco Esquivel
SlpP | MSE | Kargi Furkan (SlpP/VSL3) | Jesus Ivan Martinez Gamez
Edgar Francisco Beltran De La Torre
Jose Oscar Guevara Romero
Rodrigo Gutierrez Madrazo
Gerardo Emmanuel Lopez Lopez
Jacobo Lopez Velarde Ruiz
Luis Alberto Montes Hernandez
Jose Emmanuel Vazquez Aviles
Guillermo Adrian Ornelas Robledo
Ricardo Chindo Bear
Ricardo Fabian Corral Garcia
Jose Leobardo Gomez Lopez
Alejandra Guadalupe Gonzalez Duque
Luis Antonio Sanchez Paez
TlP | MSE | Alvarado Morales Luis Martin (TlP/MOE-PS-CC1) | Jose Alfredo Merlos Jimenez
Maria Fernanda Munguia Martinez
Sandra Karina Oro Sanchez
Gerardo Velazquez Velazquez
SlpP | CTG | Koenninger Bastian Martin (SlpP/CTG3) | Montserrat Arambula
Carla Daniela Arroyo
Aime Montserrat Fraga Guerrero
Oscar Uriel Medellin Vazquez
TlP | CTG | Verdejo Alvarado Yolanda Vanessa (TlP/CTG1) | Elizabeth Barrueta Enriquez
Artemio Alfredo Carranza De La Vega
Esperanza Del Rosario Carrillo Solis
Enya Desiree Galvez Jaimes
Maximiliano Hernandez Alamo
Viridiana Rivera Dimas
SlpP/TlP | PUQ1 | Castillo Lopez Maria Guadalupe (M/PUQ16-PS M/PUQ34-EM) | David Hernandez Araiza
Erick Alan De Santos Martinez
Cesar Ulises Hernandez Palacios
Jose Emmanuel Castillo Cadena
Eduardo Hernandez Camacho
Jorge Ernesto Hernandez Neri
Javier Jasso Lopez
Jessica Ethel Mendoza Tobias
Lizeth Pacheco Herrera
Eduardo Portillo Carmona
Victor Manuel Vazquez Morales
SlpP | PUQ2 | Galvan Rodriguez Jose Luis (M/PUQ-SlpP M/PUQ2-SlpP) | Jose Luis Galvan Rodriguez
Jorge Luis Flores Guerrero
Sandra Karina Galvan Rivera
Silvino Martinez Cruz
Hector Rodriguez Lopez
Hector De Jesus Izaguirre Hernandez
Alma Alejandra Bustamante Mayorga
Karla Mariel Gamez
Ana Paula Guerrero Martinez
Marco Antonio Gutierrez Huerta
Jorge Alberto Olivares Huerta
Juan Pablo Romero Merino
Miguel Rodriguez Leija
Berenice Del Rocio Castillo Valero
Monica Alejandra Garcia Tellez
Ana Veronica Quiroz Hernandez
Francisco Aaron Rivera Torres
Jose De Jesus Zuniga Flores
TlP | PUQ2 | Garcia Bringas Jose Alejandro (M/PUQ2-TlP) | Jose Alejandro Garcia Bringas
Leticia Lizbeth Flores Garcia
Luis Hernandez Colindres
Oscar Hernandez Martinez
Edna Scarlet Lopez Lara
Marco Antonio Valdes Rivas
Jose Hernandez Gonzalez
Cuauhtemoc Ballesteros Sanchez
Fernando Davila Esteban
Moises De Jesus Chavez
Hilario Javier Martinez Velazquez
Maria Del Carmen Pena Rayon
Omar Rosales Gonzalez
SlpP | PJM | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | German Aguilera Barragan Pickens
James Gordon
Luna Metzabeck Loza Tamez
Jorge Rocha Lopez
Oliver Alejandro Almendarez Fernandez
Juan Isidro Blanco Gonzalez
Blanca Azucena Lopez Lopez

## Projects conglomerate
Area | Location | Category | Project Title | Executive Sponsor | Project Responsible | Status Overview | Task no. | Task | Dept Resposible | Start date | Finish date | Status
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 3 | TR meeting | ChR | 2026-04-17 | 2026-04-24 | Done
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 6 | PTR parts available | PPS | 2026-07-17 | 2026-07-31 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 8 | Counter measurement | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 11 | PTR Date | LOG/ChR | 2026-08-07 | 2026-08-14 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 14 | PTR report | MFE/ENG/QMM | 2026-08-07 | 2026-08-14 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 17 | Final Review presentation | ChR | 2026-08-21 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 18 | New PN release and available in SAP | TEF6 | 2026-08-21 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-08-21 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 20 | Customer approval (full PSW) | QMM | 2026-09-04 | 2026-09-25 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 22 | Full PSW Supplier | PUQ | 2026-10-02 | 2026-10-09 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 23 | Systematic release to supplier | PPS/LOG | 2026-10-09 | 2026-10-23 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 24 | SOP supplier | PPS/LOG | 2026-10-09 | 2026-10-23 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 26 | SOP BOSCH | CFT | 2026-10-30 | 2026-10-30 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Yellow | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 3 | TR meeting | ChR | 2025-12-30 | 2025-12-30 | Done
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 6 | PTR parts available | PPS | 2026-06-26 | 2026-07-03 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 8 | Counter measurement | PUQ | 2026-07-10 | 2026-07-24 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 10 | DL review and release if applies | PUQ/ChR | 2026-07-31 | 2026-08-07 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 11 | PTR Date | LOG/ChR | 2026-08-14 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 12 | PV start date | ChR/ENG | 2026-09-18 | 2026-12-04 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 14 | PTR report | MFE/ENG/QMM | 2026-08-14 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 17 | Final Review presentation | ChR | 2026-12-11 | 2026-12-18 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 18 | New PN release and available in SAP | TEF6 | 2026-12-11 | 2026-12-18 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-12-11 | 2026-12-18 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 20 | Customer approval (full PSW) | QMM | 2026-12-11 | 2026-12-25 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 22 | Full PSW Supplier | PUQ | 2026-12-11 | CW01 2027 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 23 | Systematic release to supplier | PPS/LOG | 2027-01-15 | 2027-02-05 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 24 | SOP supplier | PPS/LOG | 2027-01-15 | 2027-02-05 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 26 | SOP BOSCH | CFT | 2027-02-12 | 2027-02-12 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | Carreira Leandro (M/PPS-CC-NA) | Ricardo Jose Vazquez Morales | Red | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 8 | Counter measurement | PUQ | 2026-01-30 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 11 | PTR Date | LOG/ChR | 2026-02-13 | 2026-02-13 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 12 | PV start date | ChR/ENG | 2026-01-30 | 2026-04-03 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 20 | Customer approval (full PSW) | QMM | 2026-02-13 | 2026-09-18 | On going
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 24 | SOP supplier | PPS/LOG | 2026-07-31 | 2026-07-31 | Plan
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 26 | SOP BOSCH | CFT | 2026-10-23 | 2026-10-23 | Plan
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 8 | Counter measurement | PUQ | 2027-02-05 | 2027-04-16 | Plan
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 11 | PTR Date | LOG/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 20 | Customer approval (full PSW) | QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 24 | SOP supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 26 | SOP BOSCH | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 8 | Counter measurement | PUQ | 2027-02-05 | 2027-04-16 | Plan
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 11 | PTR Date | LOG/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 20 | Customer approval (full PSW) | QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 24 | SOP supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 26 | SOP BOSCH | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Yellow | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 8 | Counter measurement | PUQ | 2026-01-30 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 11 | PTR Date | LOG/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 20 | Customer approval (full PSW) | QMM | 2026-02-13 | 2026-10-30 | On going
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 24 | SOP supplier | PPS/LOG | 2026-08-14 | 2026-08-14 | Plan
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 26 | SOP BOSCH | CFT | 2026-11-06 | 2026-11-06 | Plan
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | Carreira Leandro (M/PPS-CC-NA) | Lucero Villegas Toranzo | Green | 27 | ECR close ST48 | CFT |  |  | N/A
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 1 | New Set up standard alignment | CFT | 2025-10-01 | 2025-11-04 | Done
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 2 | Technical Evaluation of new standard | MFE | 2025-11-05 | 2025-11-25 | Done
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 3 | Change of documentation (set up release format) | ENG | 2025-11-26 | 2025-12-17 | Done
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 4 | New Standard implementation | ENG | 2026-05-14 | 2026-09-18 | On going
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 5 | Evaluation / Feedback of new standard | CFT | 2026-09-21 | 2026-11-02 | Plan
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 6 | Change over concept training | ENG | 2026-11-03 | 2026-11-24 | Plan
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 7 | Lessons Learned sharing | ENG | 2026-11-25 | 2026-12-01 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 1 | Business case available | ENG + PPS | 2026-03-11 | 2026-06-03 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 2 | KO meeting | ENG | 2026-05-20 | 2026-05-27 | Done
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 3 | TR meeting | ENG | 2026-05-20 | 2026-05-27 | Done
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 4 | RACE submission for new PN if applies | NA | NA | NA | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 5 | Customer acceptance of the ECR | PJM + ENG | 2026-05-27 | 2026-06-24 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 6 | PTR parts available | LOG + PPS | 2026-05-06 | 2026-06-10 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 7 | First part of MP206 completion | ENG + MFE | 2026-05-20 | 2026-06-10 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 8 | Counter measurement start date | NA | NA | NA | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 9 | Counter measurement end date | PUQ | 2026-06-10 | 2026-07-01 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 10 | DL review and release if applies | ENG + QUA | 2026-07-01 | 2026-07-08 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 11 | PTR Date | ENG + MFE | 2026-07-08 | 2026-07-15 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 12 | PV start date | ENG + MFE | 2026-07-15 | 2026-07-22 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 13 | PV end date | ENG + MFE | 2026-07-22 | 2026-08-19 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 14 | PTR and PV report | ENG | 2026-08-19 | 2026-08-26 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 15 | Interim PSW | ENG + QUA | 2026-08-26 | 2026-09-02 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 16 | Customer validation completion | PJM + ENG | 2026-09-02 | 2026-09-23 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 17 | Final Review presentation | ENG + PJM | 2026-09-23 | 2026-09-30 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 18 | New PN release and available in SAP | LOG + PPS | 2026-09-30 | 2026-10-07 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 19 | ECR ST40 | ENG | 2026-10-07 | 2026-10-14 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 20 | Customer approval (full PSW) | PJM + QUA | 2026-10-14 | 2026-10-28 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 21 | PO Update | LOG + PPS | 2026-10-28 | 2026-11-04 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 22 | Full PSW Supplier | PPS + QUA | 2026-11-04 | 2026-11-18 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 23 | Systematic release to supplier | PPS | 2026-11-18 | 2026-11-25 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 24 | SOP supplier | PPS + MFE | 2026-11-25 | 2026-12-09 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 25 | Date of first batch arrival | LOG | 2026-12-09 | 2026-12-16 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 26 | SOP BOSCH | MFE + LOG | 2026-12-16 | 2026-12-23 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Rodolfo Lopez Halun | Green | 27 | ECR close ST48 | ENG | 2026-12-23 | 2026-12-30 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 1 | Business case available | ENG + PPS + PUQ | 2026-03-02 | 2026-03-27 | Done
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 2 | KO meeting | ENG | 2026-03-30 | 2026-03-04 | Done
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 3 | TR meeting | ENG | 2026-03-30 | 2026-04-03 | Done
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 4 | Customer acceptance of the ECR | PJM + ENG | 2026-04-05 | 2026-06-05 | On going
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 5 | Parameters homologation | ENG + SUP + PUQ | 2026-06-08 | 2026-07-03 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 6 | PTR long trial for data evaluation | ENG + SUP + PUQ | 2026-07-06 | 2026-07-17 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 7 | PTR data evaluation | ENG + SUP + PUQ | 2026-07-20 | 2026-07-31 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 8 | Trial report | ENG + SUP + PUQ | 2026-08-03 | 2026-08-07 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 9 | Full PSW | ENG + PUQ + PPS | 2026-08-10 | 2026-08-28 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 10 | Final Review presentation | ENG + PJM | 2026-09-01 | 2026-09-11 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 11 | ECR ST40 (Order spec release in BOM) | ENG + DOC | 2026-09-14 | 2026-09-25 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 12 | SOP supplier | PPS + PUQ + SUP | 2026-09-28 | 2026-09-28 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Green | 13 | ECR close ST48 | ENG | 2026-09-29 | 2026-10-09 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 1 | Business case available | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 2 | KO meeting | (ChR) | 2025-04-08 | 2025-04-08 | Done
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 3 | TR meeting | (ChR) | 2025-04-12 | 2025-04-12 | Done
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 4 | RACE submission for new PN if applies | (ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 5 | Customer acceptance of the ECR | (PJM/Sales) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 6 | PTR parts available | (PPS) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 7 | First part of MP206 completion | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 8 | Counter measurement start date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 9 | Counter measurement end date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 10 | DL review and release if applies | (PUQ/ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 11 | PTR Date | (LOG/ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 12 | PV start date | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 13 | PV end date | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 14 | PTR and PV report | (MFE/ENG/QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 15 | Interim PSW | (ChR/PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 16 | Customer validation completion | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 17 | Final Review presentation | (ChR) | 2025-05-12 | 2025-05-12 | Done
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 18 | New PN release and available in SAP | (TEF6) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 19 | ECR ST40 | (ChR/Lcoal Change Co) | 30/06/2026 | 30/06/2026 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 20 | Customer approval (full PSW) | (QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 21 | PO Update | (Sales) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 22 | Full PSW Supplier | (PUQ) | 27/01/2026 | 30/06/2026 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 23 | Systematic release to supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 24 | SOP supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 25 | Date of first batch arrival | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 26 | SOP BOSCH | (CFT) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 27 | ECR close ST48 | (CFT) | 2026-10-07 | 2026-10-07 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 1 | Business case available | CFT | 2026-05-14 | 2026-06-01 | On going
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 2 | KO meeting | (ChR) | 2026-06-04 | 2026-06-18 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 3 | TR meeting | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 4 | RACE submission for new PN if applies | (ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 5 | Customer acceptance of the ECR | (PJM/Sales) | 2026-06-18 | 2026-06-25 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 6 | PTR parts available | (PPS) | 2026-10-05 | 2026-10-05 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 7 | First part of MP206 completion | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 8 | Counter measurement start date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 9 | Counter measurement end date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 10 | DL review and release if applies | (PUQ/ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 11 | PTR Date | (LOG/ChR) | 2026-10-08 | 2026-10-08 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 12 | PV start date | (ChR/ENG) | 2026-10-14 | 2026-10-14 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 13 | PV end date | (ChR/ENG) | 2027-01-20 | 2027-01-20 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 14 | PTR and PV report | (MFE/ENG/QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 15 | Interim PSW | (ChR/PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 16 | Customer validation completion | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 17 | Final Review presentation | (ChR) | 2027-01-28 | 2027-01-28 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 18 | New PN release and available in SAP | (TEF6) | 2027-02-03 | 2027-02-03 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 19 | ECR ST40 | (ChR/Lcoal Change Co) | 2027-02-03 | 2027-02-03 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 20 | Customer approval (full PSW) | (QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 21 | PO Update | (Sales) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 22 | Full PSW Supplier | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 23 | Systematic release to supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 24 | SOP supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 25 | Date of first batch arrival | (ChR) | 2027-02-10 | 2027-02-10 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 26 | SOP BOSCH | (CFT) | 2027-02-10 | 2027-02-10 | Plan
ENG | SlpP | ECR Standard | ECR: BRP New Inlet design | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez | Yellow | 27 | ECR close ST48 | (CFT) | 2027-02-10 | 2027-02-10 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 1 | Project configuration | PJM | 2025-08-15 | 2025-12-04 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 2 | QG0 | PJM | 2026-02-06 | 2026-02-06 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 3 | QG1 | PJM | 2026-04-16 | 2026-04-16 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 4 | QG4 | PJM | 2027-04-08 | 2027-04-08 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 5 | PIA-Workshop | PJM | 2025-10-06 | 2025-10-17 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 6 | PGL Assessment III | CFT | 2026-01-09 | 2026-01-09 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 7 | Release BPS for MAR | BPS Leadplant | 2026-01-14 | 2026-02-06 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 8 | MAR approved | MFE SlpP | 2026-02-20 | 2026-02-20 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 9 | Kick-off ECR-Team | QMM SlpP | 2026-02-02 | 2026-02-02 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 10 | Customer negotiation | QMM SlpP | 2026-04-17 | 2026-05-30 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 11 | Team Review | CFT | 2026-05-07 | 2026-05-07 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 12 | Design release | BMG | 2026-06-23 | 2026-06-23 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 13 | Training @ BMG6 | BMG | 2026-11-09 | 2026-12-11 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 14 | Pre-acceptance @ supplier site | MFE SlpP | 2026-11-23 | 2026-12-11 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 15 | Dismantling | BMG | 2026-12-14 | 2026-12-22 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 16 | Transport untill arrival in SlpP | MFE SlpP | 2026-12-22 | 2027-02-11 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 17 | Area & infrastructure @ SlpP | MFE SlpP | 2026-06-23 | 2026-12-20 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 18 | SlpP area ready | MFE SlpP | 2026-12-20 | 2026-12-20 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 19 | Commissioning | BMG | 2027-02-12 | 2027-03-26 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 20 | Final acceptance | MFE SlpP | 2027-03-26 | 2027-04-09 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 21 | Training @ SlpP | BMG | 2027-02-12 | 2027-04-09 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 22 | PTR / 0-series | MFE SlpP | 2027-04-09 | 2027-04-23 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 23 | P-FMEA | MFE SlpP | 2026-10-01 | 2026-10-01 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 24 | CP | MFE SlpP | 2026-11-18 | 2026-11-18 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 25 | MPF sheet | MFE SlpP | 2026-05-08 | 2026-05-08 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 26 | Safe launch plan | QMM SlpP | 2026-05-22 | 2026-05-22 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 27 | Parts tracking list | MFE SlpP | 2026-04-17 | 2026-04-17 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 28 | Production release acc. MP-206.01 | MFE SlpP | 2027-04-09 | 2027-05-01 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 29 | int. SOP | MFE SlpP | 2027-05-02 | 2027-05-02 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 30 | Measurement acc. Offer drawing | MFE SlpP | 2027-04-23 | 2027-05-07 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 31 | PPAP documentation | QMM SlpP | 2027-04-23 | 2027-05-07 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 32 | PV testing (more detailed description after commitment about strategy) | ENG | 2027-04-23 | 2027-06-04 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 33 | PPAP to customer | QMM SlpP | 2027-06-05 | 2027-06-05 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 34 | Customer release phase | MFE SlpP | 2027-06-05 | 2027-07-03 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 35 | ext. SOP | MFE SlpP | 2027-07-03 | 2027-07-03 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 36 | Safe launch incl. Ramp up support | QMM SlpP | 2027-07-03 | 2027-07-31 | Plan
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 1 | Lines Comparison | CFT | 2025-07-01 | 2025-09-30 | Done
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 2 | Business continuity of SlpP line (Spare parts) | MFE SlpP | 2025-10-01 | 2026-03-31 | Done
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 3 | Kick off | PJM_relocation | 2026-04-01 | 2026-06-30 | On going
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 4 | TEF design and refurbishment | TEF NuP | 2026-07-01 | 2027-06-30 | Plan
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 5 | Integration of SlpP types in Relocated Line | MFE SlpP / MFE NuP | 2026-04-01 | 2026-09-30 | On going
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 6 | Prepare layout | MFE SlpP | 2026-10-01 | 2027-04-01 | Plan
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 7 | Stock building at Origin | MFE NuP | 2027-07-01 | 2027-09-30 | Plan
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 8 | Shipping to SlpP | MFE NuP | 2027-10-01 | 2027-12-31 | Plan
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 9 | Re-assembly | MFE SlpP / MFE NuP | 2028-01-01 | 2028-03-31 | Plan
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 10 | Internal Release | MFE SlpP | 2028-04-01 | 2028-09-30 | Plan
MSE | SlpP | Relocation | 5NC relocation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 11 | Customer Release | MFE SlpP / QMM SlpP / QMM NuP | 2028-07-01 | 2028-12-31 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 1 | Area ready to receive the stations | BPS | 2026-01-16 | 2026-01-16 | Done
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 2 | Kick off | BPS | 2026-01-19 | 2026-01-19 | Done
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 3 | Move Molding Shaft | BPS | 2026-07-10 | 2026-07-10 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 4 | Install Coupling Unit (ST37) New | BPS | 2026-01-26 | 2026-01-26 | Done
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 5 | Move Coupling Unit (ST37) Current | BPS | 2026-08-17 | 2026-08-17 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 6 | Move Cover Ramming (St65) | BPS | 2026-09-30 | 2026-09-30 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 7 | Move Shaft C-Clip | BPS | 2026-11-20 | 2026-11-20 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | Kargi Furkan (SlpP/VSL3) | Guillermo Adrian Ornelas Robledo | Green | 8 | Move Manual Coupling Unit | BPS | 2026-11-20 | 2026-11-20 | Plan
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 1 | Business case available | ChR | 2025-01-09 | 2025-01-16 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 2 | KO meeting | ChR | 2025-04-25 | 2025-05-02 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 3 | TR meeting | ChR | 2025-04-28 | 2025-05-05 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-02-07 | 2025-02-07 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 6 | PTR parts available | PPS | 2025-04-17 | 2025-04-17 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 13 | PV end date | ChR/ENG | 2025-09-26 | 2025-09-26 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 14 | PTR and PV report | MFE/ENG/QMM | 2025-09-26 | 2025-09-26 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 15 | Interim PSW | ChR/PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 16 | Customer validation completion | ChR/ENG | 2025-09-26 | 2025-09-26 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 17 | Final Review presentation | ChR | 2026-02-13 | 2026-04-13 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 18 | New PN release and available in SAP | TEF6 | 2024-12-13 | 2024-12-13 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 20 | Customer approval full PSW | QMM | 2026-03-27 | 2026-04-24 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 21 | PO Update | Sales |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 22 | Full PSW Supplier | PUQ | 2025-04-22 | 2025-04-22 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 24 | SOP supplier | PPS/LOG | 2026-05-14 | 2026-05-14 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 25 | Date of first batch arrival | ChR | 2026-05-22 | 2026-05-22 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 26 | SOP BOSCH | CFT | 2026-05-22 | 2026-05-22 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alejandro Ceballos Sanchez | Yellow | 27 | ECR close ST48 | CFT | 2026-05-29 | 2026-05-29 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 1 | Business case available | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 2 | KO meeting | ChR | 2025-01-06 | 2025-01-17 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 3 | TR meeting | ChR | 2025-01-06 | 2025-01-17 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 4 | RACE submission for new PN if applies | ENG | 2025-01-20 | 2025-01-31 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 5 | Customer acceptance of the ECR | PJM/Sales | 2024-12-19 | 2024-12-19 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 6 | PTR parts available | PPS |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 13 | PV end date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 14 | PTR and PV report | MFE/ENG/QMM |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 15 | Interim PSW | ChR/PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 16 | Customer validation completion | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 17 | Final Review presentation | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 18 | New PN release and available in SAP | TEF6 | 2025-02-10 | 2025-02-10 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 19 | ECR ST40 | ChR/Lcoal Change Co | 2025-02-04 | 2025-02-04 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 20 | Customer approval full PSW | QMM | 2025-04-14 | 2025-04-14 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 21 | PO Update | Sales |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 22 | Full PSW Supplier | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 24 | SOP supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 25 | Date of first batch arrival | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 26 | SOP BOSCH | CFT | 2025-04-21 | 2025-04-21 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Eric Maximiliano Marmolejo Ortiz | Red | 27 | ECR close ST48 | CFT | 2025-04-21 | 2025-04-21 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 1 | Business case available | ChR | 2025-04-30 | 2025-04-30 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 2 | KO meeting | ChR | 2025-05-14 | 2025-05-14 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 3 | TR meeting | ChR | 2025-05-19 | 2025-05-19 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-06-20 | 2025-06-20 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 6 | PTR parts available | PPS |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 13 | PV end date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 14 | PTR and PV report | MFE/ENG/QMM |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 15 | Interim PSW | ChR/PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 16 | Customer validation completion | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 17 | Final Review presentation | ChR | 2025-10-24 | 2025-10-24 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 20 | Customer approval full PSW | QMM |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 21 | PO Update | Sales |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 22 | Full PSW Supplier | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 24 | SOP supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 25 | Date of first batch arrival | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 26 | SOP BOSCH | CFT | 2025-12-09 | 2025-12-09 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Yellow | 27 | ECR close ST48 | CFT |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 1 | Business case available | ChR | 2026-02-03 | 2026-02-06 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 2 | KO meeting | ChR | 2026-02-02 | 2026-02-06 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 3 | TR meeting | ChR | 2026-02-09 | 2026-02-20 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 5 | Customer acceptance of the ECR | PJM/Sales | 2026-02-09 | 2026-02-13 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 6 | PTR parts available | PPS |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 13 | PV end date | ChR/ENG | 2026-02-26 | 2026-02-26 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 14 | PTR and PV report | MFE/ENG/QMM | 2026-03-27 | 2026-03-27 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 15 | Interim PSW | ChR/PUQ | 2026-05-05 | 2026-05-05 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 16 | Customer validation completion | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 17 | Final Review presentation | ChR | 2026-04-20 | 2026-05-04 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 20 | Customer approval full PSW | QMM | 2026-06-11 | 2026-06-11 | Plan
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 21 | PO Update | Sales | 2026-02-18 | 2026-04-17 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 22 | Full PSW Supplier | PUQ |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 24 | SOP supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 25 | Date of first batch arrival | ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 26 | SOP BOSCH | CFT | 2026-06-18 | 2026-06-18 | Plan
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Alberto Levi Rossano Ruiz | Yellow | 27 | ECR close ST48 | CFT |  |  | N/A
ENG | TlP | CO ECR | ECR: 3E10177261: PS-CC/NA: Reactivation of component 6002KS0844 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 1 | KO meeting | ChR | 2026-04-29 | 2026-04-29 | Done
ENG | TlP | CO ECR | ECR: 3E10177261: PS-CC/NA: Reactivation of component 6002KS0845 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 2 | TR meeting | ChR | 2026-05-11 | 2026-05-11 | Done
ENG | TlP | CO ECR | ECR: 3E10177261: PS-CC/NA: Reactivation of component 6002KS0846 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 3 | Correction on SAP | Doc. Department | 2026-05-13 | 2026-05-13 | Done
ENG | TlP | CO ECR | ECR: 3E10177261: PS-CC/NA: Reactivation of component 6002KS0847 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 4 | ECR ST40 | ChR/Local Change Co | 2026-05-15 | 2026-05-15 | Done
ENG | TlP | CO ECR | ECR: 3E10177261: PS-CC/NA: Reactivation of component 6002KS0848 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 5 | SOP BOSCH | CFT | 2026-03-06 | 2026-03-06 | Done
ENG | TlP | CO ECR | ECR: 3E10177261: PS-CC/NA: Reactivation of component 6002KS0849 | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Diana Gabriela Cervantes Marin | Green | 6 | ECR close ST48 | Local Change Co | 2026-05-29 | 2026-05-29 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 1 | Project Award | Aq. Mngr. |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 2 | Project Kickoff | PjM | 2025-04-07 | 2025-04-07 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 3 | Design phase | ENG | 2025-06-09 |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 4 | B- Design freeze | ENG | 2025-10-02 |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 5 | QGC0 | PjM | 2025-10-02 | 2025-10-02 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 6 | Soft tooling | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 7 | B-samples production run | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 8 | B-samples | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 9 | DV | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 10 | DVP&R | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 11 | C-component design freeze | ENG | 2025-11-14 | 2025-11-14 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 12 | Drawing release | ENG | 2026-04-04 | 2026-04-04 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 13 | Sourcing | PPS | 2025-11-03 | 2025-11-28 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 14 | Line Retrofit | MSE | 2025-12-15 | 2027-02-26 | On going
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 15 | PFMEA | MSE | 2026-04-20 | 2026-08-19 | On going
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 16 | Line Release | MSE | 2026-04-27 | 2027-08-31 | On going
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 17 | 10 Digits MM | PjM | 2026-03-13 | 2026-03-13 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 18 | DFMEA | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 19 | C-component release | PUQ | 2026-11-12 | 2026-11-12 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 20 | IMDS | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 21 | MDM | PUQ/QMM |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 22 | PTR | QMM | 2026-08-14 | 2026-08-14 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 23 | PVP | QMM | 2026-08-17 | 2027-01-29 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 24 | PVP&R | QMM | 2027-02-01 | 2027-02-19 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 25 | 13 Digits release | PjM | 2026-10-23 | 2026-11-13 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 26 | Zero series | MSE / QMM |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 27 | PPAP submission | QMM | 2027-03-05 | 2027-03-05 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 28 | PPAP approval | QMM | 2027-05-18 | 2027-05-18 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 29 | QGC4 | PjM | 2027-02-15 | 2027-02-15 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Blanca Azucena Lopez Lopez | Yellow | 30 | SOP | MSE/QMM | 2027-05-18 | 2027-05-18 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 1 | Business case available | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 2 | KO meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 3 | TR meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-02-01 | 2025-02-08 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 6 | PTR parts available | PPS | 2025-05-20 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 7 | First part of MP206 completion | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 8 | Counter measurement start date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 9 | Counter measurement end date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 10 | DL review and release if applies | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 11 | Supplier Full Release | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 11 | PTR Date | LOG/ChR | 2026-06-06 | 2026-06-06 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 12 | PV start date | ChR/ENG | 2025-12-12 | 2025-12-12 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 13 | PV end date | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 14 | PTR and PV report | MFE/ENG/QMM | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 16 | Customer validation completion | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 17 | Final Review presentation | ChR | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 18 | New PN release and available in SAP | TEF6 | 2026-02-20 | 2026-02-20 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-04-21 | 2026-04-21 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 20 | 0/Series | MSE | 2026-06-01 | 2026-06-01 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 21 | PPAP Submission *from TLP to Customer | QMM | 2026-06-17 | 2026-07-14 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 22 | PPAP Approval *from Customer to TLP | QMM | 2026-07-15 | 2026-08-11 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 23 | PO Update | Sales | 2026-05-21 | 2026-05-29 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 24 | Full PSW Supplier | PUQ |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 25 | Systematic release to supplier | PPS/LOG | 2026-08-11 | 2026-08-22 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 26 | SOP supplier | PPS/LOG | 2027-01-01 | 2027-01-01 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 27 | Date of first batch arrival | ChR |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 28 | SOP BOSCH | CFT | 2026-09-04 | 2026-09-04 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 29 | ECR close ST48 | CFT |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 1 | Business case available | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 2 | KO meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 3 | TR meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 4 | RACE submission for new PN if applies | ENG | 2026-05-04 | 2026-05-18 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-02-01 | 2025-02-08 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 6 | PTR parts available | PPS | 2025-05-20 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 7 | First part of MP206 completion | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 8 | Counter measurement start date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 9 | Counter measurement end date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 10 | DL review and release if applies | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 11 | Supplier Full Release | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 11 | PTR Date | LOG/ChR | 2026-06-06 | 2026-06-06 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 12 | PV start date | ChR/ENG | 2025-12-12 | 2025-12-12 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 13 | PV end date | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 14 | PTR and PV report | MFE/ENG/QMM | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 16 | Customer validation completion | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 17 | Final Review presentation | ChR | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 18 | New PN release and available in SAP | TEF6 | 2026-02-20 | 2026-02-20 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-04-21 | 2026-04-21 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 20 | 0/Series | MSE | 2026-06-23 | 2026-06-29 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 21 | PPAP Submission *from TLP to Customer | QMM | 2026-07-14 | 2026-08-10 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 22 | PPAP Approval *from Customer to TLP | QMM | 2026-08-11 | 2026-09-07 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 23 | PO Update | Sales | 2026-05-21 | 2026-05-29 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 24 | Full PSW Supplier | PUQ |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 25 | Systematic release to supplier | PPS/LOG | 2026-08-11 | 2026-08-22 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 26 | SOP supplier | PPS/LOG |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 27 | Date of first batch arrival | ChR |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 28 | SOP BOSCH | CFT | 2026-06-29 | 2026-07-08 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 29 | ECR close ST48 | CFT |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 1 | Business case available | ChR | 2025-10-13 | 2025-10-13 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 2 | KO meeting | ChR | 2026-01-22 | 2026-01-29 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 3 | TR meeting | ChR | 2026-02-09 | 2026-02-13 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 5 | Customer acceptance of the ECR | PJM/Sales | 2026-02-13 | 2026-03-27 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 6 | PTR parts available | PPS | 2026-04-20 | 2026-05-08 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 7 | First part of MP206 completion | ChR |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 8 | Counter measurement start date | PUQ | 2026-05-22 | 2026-05-22 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 9 | Counter measurement end date | PUQ | 2026-05-29 | 2026-05-29 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 10 | DL review and release if applies | PUQ/ChR | 2026-05-29 | 2026-06-05 | On going
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 11 | Supplier Full Release | PUQ/ChR | 2026-06-05 | 2026-06-12 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 11 | PTR Date | LOG/ChR | 2026-06-01 | 2026-06-05 | On going
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 12 | PV start date | ChR/ENG | 2026-06-22 | 2026-06-22 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 13 | PV end date | ChR/ENG | 2026-07-17 | 2026-07-17 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 14 | PTR and PV report | MFE/ENG/QMM | 2026-08-14 | 2026-08-14 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 16 | Customer validation completion | ChR/ENG | 2026-08-14 | 2026-08-14 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 17 | Final Review presentation | ChR | 2026-08-14 | 2026-08-21 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 18 | New PN release and available in SAP | TEF6 | 2026-08-14 | 2026-08-14 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-07-24 | 2026-07-24 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 20 | 0/Series | MSE | 2026-07-27 | 2026-07-31 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 21 | PPAP Submission *from TLP to Customer | QMM | 2026-08-17 | 2026-09-11 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 22 | PPAP Approval *from Customer to TLP | QMM | 2026-09-14 | 2026-10-09 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 23 | PO Update | Sales | 2026-10-09 | 2026-10-09 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 24 | Full PSW Supplier | PUQ |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 25 | Systematic release to supplier | PPS/LOG | 2026-10-09 | 2026-10-09 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 26 | SOP supplier | PPS/LOG | 2026-07-02 | 2026-07-08 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 27 | Date of first batch arrival | ChR | 2026-12-01 | 2026-12-01 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 28 | SOP BOSCH | CFT | 2026-12-01 | 2026-12-01 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | Mata Rodriguez Cinthya (PS-CC/PJM-NA) | Jorge Rocha Lopez | Green | 29 | ECR close ST48 | CFT |  |  | N/A

## Sheet1
Area | Loc | Category | Project | Responsible | General status (G, Y, R)
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | Ricardo Jose Vazquez Morales | Yellow
|  |  | 3E10148721 T6 Tube (Scherdel) | Ricardo Jose Vazquez Morales | Red
|  |  | 3E10153365 (STLA) | Lucero Villegas Toranzo | Yellow
|  |  | 3E10153559 (VW) | Lucero Villegas Toranzo | Green
|  |  | 3E10153553 (Ford) | Lucero Villegas Toranzo | Yellow
|  |  | 3E10153663 (Rotax 46mm) | Lucero Villegas Toranzo | Green
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | Rodolfo Lopez Halun | Green
|  | ECR Standard | T6 - NLP Airflow, stopper design change | Rodolfo Lopez Halun | Green
|  | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Teofilo Flores Gonzalez | Green
|  | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | Diana Gabriela Cervantes Marin | Green
|  | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | Teofilo Flores Gonzalez | Yellow
MSE | SlpP | MSE Line Project | Flexline Deployment
|  | Relocation | 5NC relocation
|  | Subassembly Consolidation | Subassembly Consolidation
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | Alejandro Ceballos Sanchez | Yellow
|  | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | Eric Maximiliano Marmolejo Ortiz | Red
|  | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | Diana Gabriela Cervantes Marin | Yellow
|  | ECR Standard | ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | Alberto Levi Rossano Ruiz | Yellow
|  | CO ECR | ECR: 3E10177261: PS-CC/NA: Reactivation of component 6002KS0844 | Diana Gabriela Cervantes Marin | Green
PjM | SlpP | New Program | DVE BRP 54mm NC
| TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G
|  | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896
|  | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026