## Resource Pool Database
Location | Area | Manager | Associate
SlpP/TlP | PPS | Carreira Leandro (M/PPS-CC-NA) | Daniela Garcia Hernandez
Dario Andres Gonzalez Martinez
Amaury Martinez Garcia
Ray Edgardo Martinez Vargas
Ricardo Jose Vazquez Morales
Lucero Villegas Toranzo
SlpP | ENG | Gonzalez Bravo Jesus Ivan (PS-CC/ENG2-MX) | Teofilo Flores Gonzalez
Alejandro Antonio Lara Hernandez
Arnulfo Mauricio Serrano Alvarado
Julio Cesar Vera Vazquez
TlP |  |  | Gabriel Cruz Guzman
Alberto Levi Rossano Ruiz
SlpP | ENG | Gonzalez Loredo Jose Angel (PS-CC/ENG1-MX) | Diana Gabriela Cervantes Marin
Jose Daniel Garcia Larios
Rodolfo Lopez Halun
Carlos Alberto Monroy Medellin
Andres Navarro Chevaile
TlP |  |  | Carlos Omar Heredia Morales
Alejandro Ceballos Sanchez
Eric Maximiliano Marmolejo Ortiz
Edgar Dario Narciso Jordan
SlpP | QMM | De Souza Eduardo Henrique (PS/QMM-MSE3-SlpP) | Mauricio Anzures Enriquez
Alejandra Diaz Villela
Enny Paula Escobar Ruiz
Karen Linan Gomez
Eli Israel Mendez Lopez
Liliana Jaqueline Ramirez Quintanar
Juan Carlos Salas Sanchez
Karina Salazar Fuentes
TlP | QMM | Medina Gonzalez Fernando (EM/QMM4-Tl) | Rosario Gabriela Caltzonzin Mercado
Emerson Flores Chavez
Karla Fernanda Lechuga Gonzalez
Jesus Alejandro Ruiz Gonzalez
Alejandra Velazquez Nava
SlpP | LOD | Ovalle Juarez Aldo Cesar (SlpP/LOM SlpP/LOD1.1) | Jaime Alberto Casas Aleman Martinez
Jesus Estrada Vazquez
Luis Angel Fernandez Zapata
SlpP | LOP | Mueller Robin (SlpP/LOP2) | Pedro Alejandro Campos Martinez
Monserrat Canseco Roman
Maria Sandra Carranco Martinez
Evelyn Cerda Cerda
Harumi Anai Flores Cano
Pamela Garcia Arvizu
Jose Luis Jaramillo Merida
Ma. Elena Pruneda Castillo
Laura Isabel Torres Blanco
Carolina Valtierra Zavala
Carlos Eduardo Zavala Garcia
TlP | LOP5 | Albarran Aguirre Anayeli (TlP/LOP11) | Arturo Ivan Flores Maccise
Maria Guadalupe Hernandez Bejarano
Ana Karen Mejia Cayetano
Elsa Irma Mejia Estevez
Celia Villalobos Camacho
TLP | LOP4 | Lopez Munoz Alma Isabel (TlP/LOP4) | Natalia Gabriela Enriquez Valdez
Fabiola Hernandez Castillo
Paulina Hernandez Chavez
Pedro Arturo Lopez Martinez
Jaime Omar Marceleno Leija
Lisette Alejandra Pureco Esquivel
SlpP | MSE | Kargi Furkan (SlpP/VSL3) | Jesus Ivan Martinez Gamez
Edgar Francisco Beltran De La Torre
Jose Oscar Guevara Romero
Rodrigo Gutierrez Madrazo
Gerardo Emmanuel Lopez Lopez
Jacobo Lopez Velarde Ruiz
Luis Alberto Montes Hernandez
Jose Emmanuel Vazquez Aviles
Guillermo Adrian Ornelas Robledo
Ricardo Chindo Bear
Ricardo Fabian Corral Garcia
Jose Leobardo Gomez Lopez
Alejandra Guadalupe Gonzalez Duque
Luis Antonio Sanchez Paez
TlP | MSE | Alvarado Morales Luis Martin (TlP/MOE-PS-CC1) | Jose Alfredo Merlos Jimenez
Maria Fernanda Munguia Martinez
Sandra Karina Oro Sanchez
Gerardo Velazquez Velazquez
SlpP | CTG | Koenninger Bastian Martin (SlpP/CTG3) | Montserrat Arambula
Carla Daniela Arroyo
Aime Montserrat Fraga Guerrero
Oscar Uriel Medellin Vazquez
TlP | CTG | Verdejo Alvarado Yolanda Vanessa (TlP/CTG1) | Elizabeth Barrueta Enriquez
Artemio Alfredo Carranza De La Vega
Esperanza Del Rosario Carrillo Solis
Enya Desiree Galvez Jaimes
Maximiliano Hernandez Alamo
Viridiana Rivera Dimas
SlpP/TlP | PUQ1 | Castillo Lopez Maria Guadalupe (M/PUQ16-PS M/PUQ34-EM) | David Hernandez Araiza
Erick Alan De Santos Martinez
Cesar Ulises Hernandez Palacios
Jose Emmanuel Castillo Cadena
Eduardo Hernandez Camacho
Jorge Ernesto Hernandez Neri
Javier Jasso Lopez
Jessica Ethel Mendoza Tobias
Lizeth Pacheco Herrera
Eduardo Portillo Carmona
Victor Manuel Vazquez Morales
SlpP | PUQ2 | Galvan Rodriguez Jose Luis (M/PUQ-SlpP M/PUQ2-SlpP) | Jose Luis Galvan Rodriguez
Jorge Luis Flores Guerrero
Sandra Karina Galvan Rivera
Silvino Martinez Cruz
Hector Rodriguez Lopez
Hector De Jesus Izaguirre Hernandez
Alma Alejandra Bustamante Mayorga
Karla Mariel Gamez
Ana Paula Guerrero Martinez
Marco Antonio Gutierrez Huerta
Jorge Alberto Olivares Huerta
Juan Pablo Romero Merino
Miguel Rodriguez Leija
Berenice Del Rocio Castillo Valero
Monica Alejandra Garcia Tellez
Ana Veronica Quiroz Hernandez
Francisco Aaron Rivera Torres
Jose De Jesus Zuniga Flores
TlP | PUQ2 | Garcia Bringas Jose Alejandro (M/PUQ2-TlP) | Jose Alejandro Garcia Bringas
Leticia Lizbeth Flores Garcia
Luis Hernandez Colindres
Oscar Hernandez Martinez
Edna Scarlet Lopez Lara
Marco Antonio Valdes Rivas
Jose Hernandez Gonzalez
Cuauhtemoc Ballesteros Sanchez
Fernando Davila Esteban
Moises De Jesus Chavez
Hilario Javier Martinez Velazquez
Maria Del Carmen Pena Rayon
Omar Rosales Gonzalez

## Projects conglomerate
Area | Location | Category | Project Title | Task no. | Task | Dept Resposible | Start date | Finish date | Status
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 3 | TR meeting | ChR | 2026-04-17 | 2026-04-24 | Done
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 6 | PTR parts available | PPS | 2026-07-17 | 2026-07-31 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 8 | Counter measurement | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 11 | PTR Date | LOG/ChR | 2026-08-07 | 2026-08-14 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 14 | PTR report | MFE/ENG/QMM | 2026-08-07 | 2026-08-14 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 17 | Final Review presentation | ChR | 2026-08-21 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 18 | New PN release and available in SAP | TEF6 | 2026-08-21 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-08-21 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 20 | Customer approval (full PSW) | QMM | 2026-09-04 | 2026-09-25 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 22 | Full PSW Supplier | PUQ | 2026-10-02 | 2026-10-09 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 23 | Systematic release to supplier | PPS/LOG | 2026-10-09 | 2026-10-23 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 24 | SOP supplier | PPS/LOG | 2026-10-09 | 2026-10-23 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 26 | SOP BOSCH | CFT | 2026-10-30 | 2026-10-30 | Plan
PPS | SlpP | ECR Standard | 3E10171456 - T4EVO Cap | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 3 | TR meeting | ChR | 2025-12-30 | 2025-12-30 | Done
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 6 | PTR parts available | PPS | 2026-06-26 | 2026-07-03 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 8 | Counter measurement | PUQ | 2026-07-10 | 2026-07-24 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 10 | DL review and release if applies | PUQ/ChR | 2026-07-31 | 2026-08-07 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 11 | PTR Date | LOG/ChR | 2026-08-14 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 12 | PV start date | ChR/ENG | 2026-09-18 | 2026-12-04 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 14 | PTR report | MFE/ENG/QMM | 2026-08-14 | 2026-08-28 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 17 | Final Review presentation | ChR | 2026-12-11 | 2026-12-18 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 18 | New PN release and available in SAP | TEF6 | 2026-12-11 | 2026-12-18 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-12-11 | 2026-12-18 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 20 | Customer approval (full PSW) | QMM | 2026-12-11 | 2026-12-25 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 22 | Full PSW Supplier | PUQ | 2026-12-11 | CW01 2027 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 23 | Systematic release to supplier | PPS/LOG | 2027-01-15 | 2027-02-05 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 24 | SOP supplier | PPS/LOG | 2027-01-15 | 2027-02-05 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 26 | SOP BOSCH | CFT | 2027-02-12 | 2027-02-12 | Plan
PPS | SlpP | ECR Standard | 3E10148721 T6 Tube (Scherdel) | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 8 | Counter measurement | PUQ | 2026-01-30 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 11 | PTR Date | LOG/ChR | 2026-02-13 | 2026-02-13 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 12 | PV start date | ChR/ENG | 2026-01-30 | 2026-04-03 | Done
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 20 | Customer approval (full PSW) | QMM | 2026-02-13 | 2026-09-18 | On going
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 24 | SOP supplier | PPS/LOG | 2026-07-31 | 2026-07-31 | Plan
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 26 | SOP BOSCH | CFT | 2026-10-23 | 2026-10-23 | Plan
PPS | SlpP | ECR Standard | 3E10153365 (STLA) | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 8 | Counter measurement | PUQ | 2027-02-05 | 2027-04-16 | Plan
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 11 | PTR Date | LOG/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 20 | Customer approval (full PSW) | QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 24 | SOP supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 26 | SOP BOSCH | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153559 (VW) | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 8 | Counter measurement | PUQ | 2027-02-05 | 2027-04-16 | Plan
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 11 | PTR Date | LOG/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 20 | Customer approval (full PSW) | QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 24 | SOP supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 26 | SOP BOSCH | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153553 (Ford) | 27 | ECR close ST48 | CFT |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 1 | Business case available | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 2 | KO meeting | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 3 | TR meeting | ChR | 2026-04-10 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 5 | Customer acceptance of the ECR | PJM/Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 6 | PTR parts available | PPS | 2026-09-25 | 2026-10-16 | Plan
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 7 | First part of MP206 completion | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 8 | Counter measurement | PUQ | 2026-01-30 | 2026-04-10 | Done
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 9 | Counter measurement end date | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 11 | PTR Date | LOG/ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 12 | PV start date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 13 | PV end date | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 14 | PTR report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 14.1 | PV report | MFE/ENG/QMM |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 16 | Customer validation completion | ChR/ENG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 17 | Final Review presentation | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 20 | Customer approval (full PSW) | QMM | 2026-02-13 | 2026-10-30 | On going
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 21 | PO Update | Sales |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 22 | Full PSW Supplier | PUQ |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 24 | SOP supplier | PPS/LOG | 2026-08-14 | 2026-08-14 | Plan
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 25 | Date of first batch arrival | ChR |  |  | N/A
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 26 | SOP BOSCH | CFT | 2026-11-06 | 2026-11-06 | Plan
PPS | SlpP | ECR Standard | 3E10153663 (Rotax 46mm) | 27 | ECR close ST48 | CFT |  |  | N/A
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | 1 | New Set up standard alignment | CFT | 2025-10-01 | 2025-11-04 | Done
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | 2 | Technical Evaluation of new standard | MFE | 2025-11-05 | 2025-11-25 | Done
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | 3 | Change of documentation (set up release format) | ENG | 2025-11-26 | 2025-12-17 | Done
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | 4 | New Standard implementation | ENG | 2026-05-14 | 2026-09-18 | On going
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | 5 | Evaluation / Feedback of new standard | CFT | 2026-09-21 | 2026-11-02 | Plan
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | 6 | Change over concept training | ENG | 2026-11-03 | 2026-11-24 | Plan
ENG | SlpP | CIP Project | Ford MPC OEE Optimization | 7 | Lessons Learned sharing | ENG | 2026-11-25 | 2026-12-01 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 1 | Business case available | ENG + PPS | 2026-03-11 | 2026-06-03 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 2 | KO meeting | ENG | 2026-05-20 | 2026-05-27 | Done
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 3 | TR meeting | ENG | 2026-05-20 | 2026-05-27 | Done
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 4 | RACE submission for new PN if applies | NA | NA | NA | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 5 | Customer acceptance of the ECR | PJM + ENG | 2026-05-27 | 2026-06-24 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 6 | PTR parts available | LOG + PPS | 2026-05-06 | 2026-06-10 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 7 | First part of MP206 completion | ENG + MFE | 2026-05-20 | 2026-06-10 | On going
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 8 | Counter measurement start date | NA | NA | NA | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 9 | Counter measurement end date | PUQ | 2026-06-10 | 2026-07-01 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 10 | DL review and release if applies | ENG + QUA | 2026-07-01 | 2026-07-08 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 11 | PTR Date | ENG + MFE | 2026-07-08 | 2026-07-15 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 12 | PV start date | ENG + MFE | 2026-07-15 | 2026-07-22 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 13 | PV end date | ENG + MFE | 2026-07-22 | 2026-08-19 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 14 | PTR and PV report | ENG | 2026-08-19 | 2026-08-26 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 15 | Interim PSW | ENG + QUA | 2026-08-26 | 2026-09-02 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 16 | Customer validation completion | PJM + ENG | 2026-09-02 | 2026-09-23 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 17 | Final Review presentation | ENG + PJM | 2026-09-23 | 2026-09-30 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 18 | New PN release and available in SAP | LOG + PPS | 2026-09-30 | 2026-10-07 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 19 | ECR ST40 | ENG | 2026-10-07 | 2026-10-14 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 20 | Customer approval (full PSW) | PJM + QUA | 2026-10-14 | 2026-10-28 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 21 | PO Update | LOG + PPS | 2026-10-28 | 2026-11-04 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 22 | Full PSW Supplier | PPS + QUA | 2026-11-04 | 2026-11-18 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 23 | Systematic release to supplier | PPS | 2026-11-18 | 2026-11-25 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 24 | SOP supplier | PPS + MFE | 2026-11-25 | 2026-12-09 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 25 | Date of first batch arrival | LOG | 2026-12-09 | 2026-12-16 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 26 | SOP BOSCH | MFE + LOG | 2026-12-16 | 2026-12-23 | Plan
ENG | SlpP | ECR Standard | T6 - NLP Airflow, stopper design change | 27 | ECR close ST48 | ENG | 2026-12-23 | 2026-12-30 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 1 | Business case available | ENG + PPS + PUQ | 2026-03-02 | 2026-03-27 | Done
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 2 | KO meeting | ENG | 2026-03-30 | 2026-03-04 | Done
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 3 | TR meeting | ENG | 2026-03-30 | 2026-04-03 | Done
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 4 | Customer acceptance of the ECR | PJM + ENG | 2026-04-05 | 2026-06-05 | On going
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 5 | Parameters homologation | ENG + SUP + PUQ | 2026-06-08 | 2026-07-03 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 6 | PTR long trial for data evaluation | ENG + SUP + PUQ | 2026-07-06 | 2026-07-17 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 7 | PTR data evaluation | ENG + SUP + PUQ | 2026-07-20 | 2026-07-31 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 8 | Trial report | ENG + SUP + PUQ | 2026-08-03 | 2026-08-07 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 9 | Full PSW | ENG + PUQ + PPS | 2026-08-10 | 2026-08-28 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 10 | Final Review presentation | ENG + PJM | 2026-09-01 | 2026-09-11 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 11 | ECR ST40 (Order spec release in BOM) | ENG + DOC | 2026-09-14 | 2026-09-25 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 12 | SOP supplier | PPS + PUQ + SUP | 2026-09-28 | 2026-09-28 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 13 | ECR close ST48 | ENG | 2026-09-29 | 2026-10-09 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 1 | Business case available | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 2 | KO meeting | (ChR) | 2025-04-08 | 2025-04-08 | Done
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 3 | TR meeting | (ChR) | 2025-04-12 | 2025-04-12 | Done
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 4 | RACE submission for new PN if applies | (ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 5 | Customer acceptance of the ECR | (PJM/Sales) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 6 | PTR parts available | (PPS) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 7 | First part of MP206 completion | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 8 | Counter measurement start date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 9 | Counter measurement end date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 10 | DL review and release if applies | (PUQ/ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 11 | PTR Date | (LOG/ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 12 | PV start date | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 13 | PV end date | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 14 | PTR and PV report | (MFE/ENG/QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 15 | Interim PSW | (ChR/PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 16 | Customer validation completion | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 17 | Final Review presentation | (ChR) | 2025-05-12 | 2025-05-12 | Done
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 18 | New PN release and available in SAP | (TEF6) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 19 | ECR ST40 | (ChR/Lcoal Change Co) | 30/06/2026 | 30/06/2026 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 20 | Customer approval (full PSW) | (QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 21 | PO Update | (Sales) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 22 | Full PSW Supplier | (PUQ) | 27/01/2026 | 30/06/2026 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 23 | Systematic release to supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 24 | SOP supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 25 | Date of first batch arrival | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 26 | SOP BOSCH | (CFT) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update | 27 | ECR close ST48 | (CFT) | 2026-10-07 | 2026-10-07 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 1 | Business case available | CFT | 2026-05-14 | 2026-06-01 | On going
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 2 | KO meeting | (ChR) | 2026-06-04 | 2026-06-18 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 3 | TR meeting | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 4 | RACE submission for new PN if applies | (ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 5 | Customer acceptance of the ECR | (PJM/Sales) | 2026-06-18 | 2026-06-25 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 6 | PTR parts available | (PPS) | 2026-10-05 | 2026-10-05 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 7 | First part of MP206 completion | (ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 8 | Counter measurement start date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 9 | Counter measurement end date | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 10 | DL review and release if applies | (PUQ/ChR) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 11 | PTR Date | (LOG/ChR) | 2026-10-08 | 2026-10-08 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 12 | PV start date | (ChR/ENG) | 2026-10-14 | 2026-10-14 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 13 | PV end date | (ChR/ENG) | 2027-01-20 | 2027-01-20 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 14 | PTR and PV report | (MFE/ENG/QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 15 | Interim PSW | (ChR/PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 16 | Customer validation completion | (ChR/ENG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 17 | Final Review presentation | (ChR) | 2027-01-28 | 2027-01-28 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 18 | New PN release and available in SAP | (TEF6) | 2027-02-03 | 2027-02-03 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 19 | ECR ST40 | (ChR/Lcoal Change Co) | 2027-02-03 | 2027-02-03 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 20 | Customer approval (full PSW) | (QMM) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 21 | PO Update | (Sales) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 22 | Full PSW Supplier | (PUQ) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 23 | Systematic release to supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 24 | SOP supplier | (PPS/LOG) |  |  | N/A
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 25 | Date of first batch arrival | (ChR) | 2027-02-10 | 2027-02-10 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 26 | SOP BOSCH | (CFT) | 2027-02-10 | 2027-02-10 | Plan
ENG | SlpP | ECR Standard | ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL | 27 | ECR close ST48 | (CFT) | 2027-02-10 | 2027-02-10 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 1 | Project configuration | PJM | 2025-08-15 | 2025-12-04 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 2 | QG0 | PJM | 2026-02-06 | 2026-02-06 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 3 | QG1 | PJM | 2026-04-16 | 2026-04-16 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 4 | QG4 | PJM | 2027-04-08 | 2027-04-08 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 5 | PIA-Workshop | PJM | 2025-10-06 | 2025-10-17 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 6 | PGL Assessment III | CFT | 2026-01-09 | 2026-01-09 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 7 | Release BPS for MAR | BPS Leadplant | 2026-01-14 | 2026-02-06 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 8 | MAR approved | MFE SlpP | 2026-02-20 | 2026-02-20 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 9 | Kick-off ECR-Team | QMM SlpP | 2026-02-02 | 2026-02-02 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 10 | Customer negotiation | QMM SlpP | 2026-04-17 | 2026-05-30 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 11 | Team Review | CFT | 2026-05-07 | 2026-05-07 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 12 | Design release | BMG | 2026-06-23 | 2026-06-23 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 13 | Training @ BMG6 | BMG | 2026-11-09 | 2026-12-11 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 14 | Pre-acceptance @ supplier site | MFE SlpP | 2026-11-23 | 2026-12-11 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 15 | Dismantling | BMG | 2026-12-14 | 2026-12-22 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 16 | Transport untill arrival in SlpP | MFE SlpP | 2026-12-22 | 2027-02-11 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 17 | Area & infrastructure @ SlpP | MFE SlpP | 2026-06-23 | 2026-12-20 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 18 | SlpP area ready | MFE SlpP | 2026-12-20 | 2026-12-20 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 19 | Commissioning | BMG | 2027-02-12 | 2027-03-26 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 20 | Final acceptance | MFE SlpP | 2027-03-26 | 2027-04-09 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 21 | Training @ SlpP | BMG | 2027-02-12 | 2027-04-09 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 22 | PTR / 0-series | MFE SlpP | 2027-04-09 | 2027-04-23 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 23 | P-FMEA | MFE SlpP | 2026-10-01 | 2026-10-01 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 24 | CP | MFE SlpP | 2026-11-18 | 2026-11-18 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 25 | MPF sheet | MFE SlpP | 2026-05-08 | 2026-05-08 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 26 | Safe launch plan | QMM SlpP | 2026-05-22 | 2026-05-22 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 27 | Parts tracking list | MFE SlpP | 2026-04-17 | 2026-04-17 | Done
MSE | SlpP | MSE Line Project | Flexline Deployment | 28 | Production release acc. MP-206.01 | MFE SlpP | 2027-04-09 | 2027-05-01 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 29 | int. SOP | MFE SlpP | 2027-05-02 | 2027-05-02 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 30 | Measurement acc. Offer drawing | MFE SlpP | 2027-04-23 | 2027-05-07 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 31 | PPAP documentation | QMM SlpP | 2027-04-23 | 2027-05-07 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 32 | PV testing (more detailed description after commitment about strategy) | ENG | 2027-04-23 | 2027-06-04 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 33 | PPAP to customer | QMM SlpP | 2027-06-05 | 2027-06-05 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 34 | Customer release phase | MFE SlpP | 2027-06-05 | 2027-07-03 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 35 | ext. SOP | MFE SlpP | 2027-07-03 | 2027-07-03 | Plan
MSE | SlpP | MSE Line Project | Flexline Deployment | 36 | Safe launch incl. Ramp up support | QMM SlpP | 2027-07-03 | 2027-07-31 | Plan
MSE | SlpP | Relocation | 5NC relocation | 1 | Lines Comparison | CFT | 2025-07-01 | 2025-09-30 | Done
MSE | SlpP | Relocation | 5NC relocation | 2 | Business continuity of SlpP line (Spare parts) | MFE SlpP | 2025-10-01 | 2026-03-31 | Done
MSE | SlpP | Relocation | 5NC relocation | 3 | Kick off | PJM_relocation | 2026-04-01 | 2026-06-30 | On going
MSE | SlpP | Relocation | 5NC relocation | 4 | TEF design and refurbishment | TEF NuP | 2026-07-01 | 2027-06-30 | Plan
MSE | SlpP | Relocation | 5NC relocation | 5 | Integration of SlpP types in Relocated Line | MFE SlpP / MFE NuP | 2026-04-01 | 2026-09-30 | On going
MSE | SlpP | Relocation | 5NC relocation | 6 | Prepare layout | MFE SlpP | 2026-10-01 | 2027-04-01 | Plan
MSE | SlpP | Relocation | 5NC relocation | 7 | Stock building at Origin | MFE NuP | 2027-07-01 | 2027-09-30 | Plan
MSE | SlpP | Relocation | 5NC relocation | 8 | Shipping to SlpP | MFE NuP | 2027-10-01 | 2027-12-31 | Plan
MSE | SlpP | Relocation | 5NC relocation | 9 | Re-assembly | MFE SlpP / MFE NuP | 2028-01-01 | 2028-03-31 | Plan
MSE | SlpP | Relocation | 5NC relocation | 10 | Internal Release | MFE SlpP | 2028-04-01 | 2028-09-30 | Plan
MSE | SlpP | Relocation | 5NC relocation | 11 | Customer Release | MFE SlpP / QMM SlpP / QMM NuP | 2028-07-01 | 2028-12-31 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 1 | Area ready to receive the stations | BPS | 2026-01-16 | 2026-01-16 | Done
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 2 | Kick off | BPS | 2026-01-19 | 2026-01-19 | Done
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 3 | Move Molding Shaft | BPS | 2026-07-10 | 2026-07-10 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 4 | Install Coupling Unit (ST37) New | BPS | 2026-01-26 | 2026-01-26 | Done
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 5 | Move Coupling Unit (ST37) Current | BPS | 2026-08-17 | 2026-08-17 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 6 | Move Cover Ramming (St65) | BPS | 2026-09-30 | 2026-09-30 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 7 | Move Shaft C-Clip | BPS | 2026-11-20 | 2026-11-20 | Plan
MSE | SlpP | Subassembly Consolidation | Subassembly Consolidation | 8 | Move Manual Coupling Unit | BPS | 2026-11-20 | 2026-11-20 | Plan
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 1 | Business case available | ChR | 2025-01-09 | 2025-01-16 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 2 | KO meeting | ChR | 2025-04-25 | 2025-05-02 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 3 | TR meeting | ChR | 2025-04-28 | 2025-05-05 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-02-07 | 2025-02-07 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 6 | PTR parts available | PPS | 2025-04-17 | 2025-04-17 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 13 | PV end date | ChR/ENG | 2025-09-26 | 2025-09-26 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 14 | PTR and PV report | MFE/ENG/QMM | 2025-09-26 | 2025-09-26 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 15 | Interim PSW | ChR/PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 16 | Customer validation completion | ChR/ENG | 2025-09-26 | 2025-09-26 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 17 | Final Review presentation | ChR | 2026-02-13 | 2026-04-13 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 18 | New PN release and available in SAP | TEF6 | 2024-12-13 | 2024-12-13 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 20 | Customer approval full PSW | QMM | 2026-03-27 | 2026-04-24 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 21 | PO Update | Sales |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 22 | Full PSW Supplier | PUQ | 2025-04-22 | 2025-04-22 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 24 | SOP supplier | PPS/LOG | 2026-05-14 | 2026-05-14 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 25 | Date of first batch arrival | ChR | 2026-05-22 | 2026-05-22 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 26 | SOP BOSCH | CFT | 2026-05-22 | 2026-05-22 | Done
ENG | TlP | ECR Standard | ECR: 3E10128035 BASF material discontinuation 6002KP0673 | 27 | ECR close ST48 | CFT | 2026-05-29 | 2026-05-29 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 1 | Business case available | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 2 | KO meeting | ChR | 2025-01-06 | 2025-01-17 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 3 | TR meeting | ChR | 2025-01-06 | 2025-01-17 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 4 | RACE submission for new PN if applies | ENG | 2025-01-20 | 2025-01-31 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 5 | Customer acceptance of the ECR | PJM/Sales | 2024-12-19 | 2024-12-19 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 6 | PTR parts available | PPS |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 13 | PV end date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 14 | PTR and PV report | MFE/ENG/QMM |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 15 | Interim PSW | ChR/PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 16 | Customer validation completion | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 17 | Final Review presentation | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 18 | New PN release and available in SAP | TEF6 | 2025-02-10 | 2025-02-10 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 19 | ECR ST40 | ChR/Lcoal Change Co | 2025-02-04 | 2025-02-04 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 20 | Customer approval full PSW | QMM | 2025-04-14 | 2025-04-14 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 21 | PO Update | Sales |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 22 | Full PSW Supplier | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 24 | SOP supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 25 | Date of first batch arrival | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 26 | SOP BOSCH | CFT | 2025-04-21 | 2025-04-21 | Done
ENG | TlP | ECR Standard | ECR: 3E10141881 002KP0363 change to 158742000F | 27 | ECR close ST48 | CFT | 2025-04-21 | 2025-04-21 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 1 | Business case available | ChR | 2025-04-30 | 2025-04-30 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 2 | KO meeting | ChR | 2025-05-14 | 2025-05-14 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 3 | TR meeting | ChR | 2025-05-19 | 2025-05-19 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-06-20 | 2025-06-20 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 6 | PTR parts available | PPS |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 13 | PV end date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 14 | PTR and PV report | MFE/ENG/QMM |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 15 | Interim PSW | ChR/PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 16 | Customer validation completion | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 17 | Final Review presentation | ChR | 2025-10-24 | 2025-10-24 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 20 | Customer approval full PSW | QMM |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 21 | PO Update | Sales |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 22 | Full PSW Supplier | PUQ |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 24 | SOP supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 25 | Date of first batch arrival | ChR |  |  | N/A
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 26 | SOP BOSCH | CFT | 2025-12-09 | 2025-12-09 | Done
ENG | TlP | ECR Standard | ECR: 3E10155743 Cancellation of Part numbers Ford | 27 | ECR close ST48 | CFT |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 1 | Business case available | ChR | 2026-02-03 | 2026-02-06 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 2 | KO meeting | ChR | 2026-02-02 | 2026-02-06 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 3 | TR meeting | ChR | 2026-02-09 | 2026-02-20 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 5 | Customer acceptance of the ECR | PJM/Sales | 2026-02-09 | 2026-02-13 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 6 | PTR parts available | PPS |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 7 | First part of MP206 completion | ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 8 | Counter measurement start date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 9 | Counter measurement end date | PUQ |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 10 | DL review and release if applies | PUQ/ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 11 | PTR Date | LOG/ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 12 | PV start date | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 13 | PV end date | ChR/ENG | 2026-02-26 | 2026-02-26 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 14 | PTR and PV report | MFE/ENG/QMM | 2026-03-27 | 2026-03-27 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 15 | Interim PSW | ChR/PUQ | 2026-05-05 | 2026-05-05 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 16 | Customer validation completion | ChR/ENG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 17 | Final Review presentation | ChR | 2026-04-20 | 2026-05-04 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 18 | New PN release and available in SAP | TEF6 |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 19 | ECR ST40 | ChR/Lcoal Change Co |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 20 | Customer approval full PSW | QMM | 2026-06-11 | 2026-06-11 | Plan
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 21 | PO Update | Sales | 2026-02-18 | 2026-04-17 | Done
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 22 | Full PSW Supplier | PUQ |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 23 | Systematic release to supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 24 | SOP supplier | PPS/LOG |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 25 | Date of first batch arrival | ChR |  |  | N/A
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 26 | SOP BOSCH | CFT | 2026-06-18 | 2026-06-18 | Plan
ENG | TlP | ECR Standard | Project / ECR: 3E10175353 BRP Sea/Doo FSMs /Updates per customer request 2nd label | 27 | ECR close ST48 | CFT |  |  | N/A
ENG | TlP | CO ECR | NO NAME | 1 | KO meeting | ChR | 2026-04-29 | 2026-04-29 | Done
ENG | TlP | CO ECR | NO NAME | 2 | TR meeting | ChR | 2026-05-11 | 2026-05-11 | Done
ENG | TlP | CO ECR | NO NAME | 3 | Correction on SAP | Doc. Department | 2026-05-13 | 2026-05-13 | Done
ENG | TlP | CO ECR | NO NAME | 4 | ECR ST40 | ChR/Local Change Co | 2026-05-15 | 2026-05-15 | Done
ENG | TlP | CO ECR | NO NAME | 5 | SOP BOSCH | CFT | 2026-03-06 | 2026-03-06 | Done
ENG | TlP | CO ECR | NO NAME | 6 | ECR close ST48 | Local Change Co | 2026-05-29 | 2026-05-29 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | 1 | Project Award | Aq. Mngr. |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 2 | Project Kickoff | PjM | 2025-04-07 | 2025-04-07 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | 3 | Design phase | ENG | 2025-06-09 |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 4 | B- Design freeze | ENG | 2025-10-02 |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 5 | QGC0 | PjM | 2025-10-02 | 2025-10-02 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | 6 | Soft tooling | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 7 | B-samples production run | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 8 | B-samples | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 9 | DV | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 10 | DVP&R | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 11 | C-component design freeze | ENG | 2025-11-14 | 2025-11-14 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | 12 | Drawing release | ENG | 2026-04-04 | 2026-04-04 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | 13 | Sourcing | PPS | 2025-11-03 | 2025-11-28 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | 14 | Line Retrofit | MSE | 2025-12-15 | 2027-02-26 | On going
PjM | SlpP | New Program | DVE BRP 54mm NC | 15 | PFMEA | MSE | 2026-04-20 | 2026-08-19 | On going
PjM | SlpP | New Program | DVE BRP 54mm NC | 16 | Line Release | MSE | 2026-04-27 | 2027-08-31 | On going
PjM | SlpP | New Program | DVE BRP 54mm NC | 17 | 10 Digits MM | PjM | 2026-03-13 | 2026-03-13 | Done
PjM | SlpP | New Program | DVE BRP 54mm NC | 18 | DFMEA | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 19 | C-component release | PUQ | 2026-11-12 | 2026-11-12 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 20 | IMDS | ENG |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 21 | MDM | PUQ/QMM |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 22 | PTR | QMM | 2026-08-14 | 2026-08-14 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 23 | PVP | QMM | 2026-08-17 | 2027-01-29 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 24 | PVP&R | QMM | 2027-02-01 | 2027-02-19 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 25 | 13 Digits release | PjM | 2026-10-23 | 2026-11-13 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 26 | Zero series | MSE / QMM |  |  | N/A
PjM | SlpP | New Program | DVE BRP 54mm NC | 27 | PPAP submission | QMM | 2027-03-05 | 2027-03-05 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 28 | PPAP approval | QMM | 2027-05-18 | 2027-05-18 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 29 | QGC4 | PjM | 2027-02-15 | 2027-02-15 | Plan
PjM | SlpP | New Program | DVE BRP 54mm NC | 30 | SOP | MSE/QMM | 2027-05-18 | 2027-05-18 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 1 | Business case available | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 2 | KO meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 3 | TR meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-02-01 | 2025-02-08 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 6 | PTR parts available | PPS | 2025-05-20 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 7 | First part of MP206 completion | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 8 | Counter measurement start date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 9 | Counter measurement end date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 10 | DL review and release if applies | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 11 | Supplier Full Release | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 11 | PTR Date | LOG/ChR | 2026-06-06 | 2026-06-06 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 12 | PV start date | ChR/ENG | 2025-12-12 | 2025-12-12 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 13 | PV end date | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 14 | PTR and PV report | MFE/ENG/QMM | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 16 | Customer validation completion | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 17 | Final Review presentation | ChR | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 18 | New PN release and available in SAP | TEF6 | 2026-02-20 | 2026-02-20 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-04-21 | 2026-04-21 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 20 | 0/Series | MSE | 2026-06-01 | 2026-06-01 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 21 | PPAP Submission *from TLP to Customer | QMM | 2026-06-17 | 2026-07-14 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 22 | PPAP Approval *from Customer to TLP | QMM | 2026-07-15 | 2026-08-11 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 23 | PO Update | Sales | 2026-05-21 | 2026-05-29 | Done
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 24 | Full PSW Supplier | PUQ |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 25 | Systematic release to supplier | PPS/LOG | 2026-08-11 | 2026-08-22 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 26 | SOP supplier | PPS/LOG | 2027-01-01 | 2027-01-01 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 27 | Date of first batch arrival | ChR |  |  | N/A
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 28 | SOP BOSCH | CFT | 2026-09-04 | 2026-09-04 | Plan
PjM | TlP | ECR Standard | ECR 3E10144732 – Pump para 2154 -> 0580.454.00U → 0580.454.01G | 29 | ECR close ST48 | CFT |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 1 | Business case available | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 2 | KO meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 3 | TR meeting | ChR | 2025-01-01 | 2025-01-01 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 4 | RACE submission for new PN if applies | ENG | 2026-05-04 | 2026-05-18 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 5 | Customer acceptance of the ECR | PJM/Sales | 2025-02-01 | 2025-02-08 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 6 | PTR parts available | PPS | 2025-05-20 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 7 | First part of MP206 completion | ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 8 | Counter measurement start date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 9 | Counter measurement end date | PUQ | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 10 | DL review and release if applies | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 11 | Supplier Full Release | PUQ/ChR | 2025-05-26 | 2025-05-26 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 11 | PTR Date | LOG/ChR | 2026-06-06 | 2026-06-06 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 12 | PV start date | ChR/ENG | 2025-12-12 | 2025-12-12 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 13 | PV end date | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 14 | PTR and PV report | MFE/ENG/QMM | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 16 | Customer validation completion | ChR/ENG | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 17 | Final Review presentation | ChR | 2026-04-14 | 2026-04-14 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 18 | New PN release and available in SAP | TEF6 | 2026-02-20 | 2026-02-20 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-04-21 | 2026-04-21 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 20 | 0/Series | MSE | 2026-06-23 | 2026-06-29 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 21 | PPAP Submission *from TLP to Customer | QMM | 2026-07-14 | 2026-08-10 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 22 | PPAP Approval *from Customer to TLP | QMM | 2026-08-11 | 2026-09-07 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 23 | PO Update | Sales | 2026-05-21 | 2026-05-29 | Done
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 24 | Full PSW Supplier | PUQ |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 25 | Systematic release to supplier | PPS/LOG | 2026-08-11 | 2026-08-22 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 26 | SOP supplier | PPS/LOG |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 27 | Date of first batch arrival | ChR |  |  | N/A
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 28 | SOP BOSCH | CFT | 2026-06-29 | 2026-07-08 | Plan
PjM | TlP | ECR Standard | RACE FXRC126580 – Pump para 1895 & RACE FXRC126584 – Pump para 1896 | 29 | ECR close ST48 | CFT |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 1 | Business case available | ChR | 2025-10-13 | 2025-10-13 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 2 | KO meeting | ChR | 2026-01-22 | 2026-01-29 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 3 | TR meeting | ChR | 2026-02-09 | 2026-02-13 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 4 | RACE submission for new PN if applies | ENG |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 5 | Customer acceptance of the ECR | PJM/Sales | 2026-02-13 | 2026-03-27 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 6 | PTR parts available | PPS | 2026-04-20 | 2026-05-08 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 7 | First part of MP206 completion | ChR |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 8 | Counter measurement start date | PUQ | 2026-05-22 | 2026-05-22 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 9 | Counter measurement end date | PUQ | 2026-05-29 | 2026-05-29 | Done
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 10 | DL review and release if applies | PUQ/ChR | 2026-05-29 | 2026-06-05 | On going
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 11 | Supplier Full Release | PUQ/ChR | 2026-06-05 | 2026-06-12 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 11 | PTR Date | LOG/ChR | 2026-06-01 | 2026-06-05 | On going
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 12 | PV start date | ChR/ENG | 2026-06-22 | 2026-06-22 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 13 | PV end date | ChR/ENG | 2026-07-17 | 2026-07-17 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 14 | PTR and PV report | MFE/ENG/QMM | 2026-08-14 | 2026-08-14 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 15 | Interim PSW | ChR/PUQ |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 16 | Customer validation completion | ChR/ENG | 2026-08-14 | 2026-08-14 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 17 | Final Review presentation | ChR | 2026-08-14 | 2026-08-21 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 18 | New PN release and available in SAP | TEF6 | 2026-08-14 | 2026-08-14 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 19 | ECR ST40 | ChR/Lcoal Change Co | 2026-07-24 | 2026-07-24 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 20 | 0/Series | MSE | 2026-07-27 | 2026-07-31 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 21 | PPAP Submission *from TLP to Customer | QMM | 2026-08-17 | 2026-09-11 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 22 | PPAP Approval *from Customer to TLP | QMM | 2026-09-14 | 2026-10-09 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 23 | PO Update | Sales | 2026-10-09 | 2026-10-09 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 24 | Full PSW Supplier | PUQ |  |  | N/A
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 25 | Systematic release to supplier | PPS/LOG | 2026-10-09 | 2026-10-09 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 26 | SOP supplier | PPS/LOG | 2026-07-02 | 2026-07-08 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 27 | Date of first batch arrival | ChR | 2026-12-01 | 2026-12-01 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 28 | SOP BOSCH | CFT | 2026-12-01 | 2026-12-01 | Plan
PjM | TlP | ECR Standard | 3E10165605 – Nissan & STLA Reservoir – 2026 | 29 | ECR close ST48 | CFT |  |  | N/A