## New Program (hidden)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Project Award
2 | Project Kickoff
3 | Design phase
4 | Drawing release
5 | B- Design freeze
6 | Soft tooling
7 | B-samples production run
8 | B-samples
9 | DV
10 | DVP&R
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## CIP - MPC OEE
Project: Ford MPC OEE Optimization
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs) | Comments
1 | New Set up standard alignment | CFT | 2025-10-01 | 5 | 2025-11-04 |  |  | Feasibility and CFT agreement
2 | Technical Evaluation of new standard | MFE | 2025-11-05 | 3 | 2025-11-25 | * Edge break measurements | 15 | PTRs with samples with new condition, supplier feedback
3 | Change of documentation (set up release format) | ENG | 2025-11-26 | 3 | 2025-12-17 | * ENG Lead development reviews * Data on how is performed in SlpP, machinning plate line | 15 | Creation of new order specification
4 | New Standard implementation | ENG | 2026-05-14 | 16 | 2026-09-18 | * Business case for supplier * Business case for implementation inhouse | 10 | Ongoing, ECR, order specification, Document updated, Control plan. * Estimated start and finish date with the premise that decision to move forward according to business case for brushing process at supplier is completed within the next 2 weeks.
5 | Evaluation / Feedback of new standard | CFT | 2026-09-21 | 6 | 2026-11-02 | *New standard implemented | 10 | Confirmation after implementation, Capability
6 | Change over concept training | ENG | 2026-11-03 | 3 | 2026-11-24 |  | 10 | Change well documented
7 | Lessons Learned sharing | ENG | 2026-11-25 | 1 | 2026-12-01 |  | 10 | Adding to design check list for DV-E's

## ECR - Standard - T6 NLP
Project / ECR: 3EXXXXXXXXX: T6 - NLP Airflow, stopper design change
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs) | Comments
1 | Business case available | ENG + PPS | 2026-03-11 | 5 | 2026-06-03 | * Supplier feasibility *Task force activities, customer meetings * Quotation for the change from supplier * Updated drawing | 45
2 | KO meeting | ENG | 2026-05-20 | 1 | 2026-05-27 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25
3 | TR meeting | ENG | 2026-05-20 | 1 | 2026-05-27 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25
4 | RACE submission for new PN if applies | NA | NA | NA | NA | NA | NA
5 | Customer acceptance of the ECR | PJM + ENG | 2026-05-27 | 4 | 2026-06-24 | * Customer technical meetings * Design definition | 15
6 | PTR parts available | LOG + PPS | 2026-05-06 | 5 | 2026-06-10 | * Updated Drawing * Feasilibity confirmation * Purchasing Order | 20
7 | First part of MP206 completion | ENG + MFE | 2026-05-20 | 3 | 2026-06-10 | * PTR parts * Manufacturing setup | 30
8 | Counter measurement start date | NA | NA | NA | NA | NA | NA
9 | Counter measurement end date | PUQ | 2026-06-10 | 3 | 2026-07-01 | * Counter measurement data * Analysis results | 20
10 | DL review and release if applies | ENG + QUA | 2026-07-01 | 1 | 2026-07-08 | * QMM Test results * PTR results (EoL test, airflow) * DL with proposed deviations | 15
11 | PTR Date | ENG + MFE | 2026-07-08 | 1 | 2026-07-15 | * Pieces available with the machined LMS at 15.3° | 10
12 | PV start date | ENG + MFE | 2026-07-15 | 1 | 2026-07-22 | * PTR approval * Pieces available within specification | 15
13 | PV end date | ENG + MFE | 2026-07-22 | 4 | 2026-08-19 | * Production validation tests | 25
14 | PTR and PV report | ENG | 2026-08-19 | 1 | 2026-08-26 | * All test data * Validation results * Teardown Analysis | 20
15 | Interim PSW | ENG + QUA | 2026-08-26 | 1 | 2026-09-02 | * PTR report * PV report | 15
16 | Customer validation completion | PJM + ENG | 2026-09-02 | 3 | 2026-09-23 | * Interim PSW * Customer testing | 20
17 | Final Review presentation | ENG + PJM | 2026-09-23 | 1 | 2026-09-30 | * All validation data | 25
18 | New PN release and available in SAP | LOG + PPS | 2026-09-30 | 1 | 2026-10-07 | * Final approval | 10
19 | ECR ST40 | ENG | 2026-10-07 | 1 | 2026-10-14 | * PN release confirmation | 5
20 | Customer approval (full PSW) | PJM + QUA | 2026-10-14 | 2 | 2026-10-28 | * Complete documentation | 15
21 | PO Update | LOG + PPS | 2026-10-28 | 1 | 2026-11-04 | * Customer approval | 5
22 | Full PSW Supplier | PPS + QUA | 2026-11-04 | 2 | 2026-11-18 | * All documentation | 20
23 | Systematic release to supplier | PPS | 2026-11-18 | 1 | 2026-11-25 | * Full PSW complete | 10
24 | SOP supplier | PPS + MFE | 2026-11-25 | 2 | 2026-12-09 | * Production readiness | 25
25 | Date of first batch arrival | LOG | 2026-12-09 | 1 | 2026-12-16 | * SOP confirmation | 5
26 | SOP BOSCH | MFE + LOG | 2026-12-16 | 1 | 2026-12-23 | * First batch received | 15
27 | ECR close ST48 | ENG | 2026-12-23 | 1 | 2026-12-30 | * SOP complete | 5

## ECR - Standard - T4 Leakage
Project / ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs) | Comments
1 | Business case available | ENG + PPS + PUQ | 2026-03-02 | 4 | 2026-03-27 | * Supplier feasibility *Task force activities, customer meetings * Quotation for the change from supplier * Updated drawing/order specification | 30
2 | KO meeting | ENG | 2026-03-30 | 1 | 2026-03-04 | *ECR creation * Updated drawing/order specification * Customer/ECR presentation * CTG Checklist | 20
3 | TR meeting | ENG | 2026-03-30 | 1 | 2026-04-03 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 20
4 | Customer acceptance of the ECR | PJM + ENG | 2026-04-05 | 4 | 2026-06-05 | * Customer technical meetings * Order specification parameters definition | 15
5 | Parameters homologation | ENG + SUP + PUQ | 2026-06-08 | 4 | 2026-07-03 | * Parameters definition * Trials | 30
6 | PTR long trial for data evaluation | ENG + SUP + PUQ | 2026-07-06 | 2 | 2026-07-17 | * PTR 1 week. | 20
7 | PTR data evaluation | ENG + SUP + PUQ | 2026-07-20 | 2 | 2026-07-31 | * Evaluation for scrap % * Evaluation of Cg/CgK | 20
8 | Trial report | ENG + SUP + PUQ | 2026-08-03 | 1 | 2026-08-07 | * All test data * Validation results | 20
9 | Full PSW | ENG + PUQ + PPS | 2026-08-10 | 3 | 2026-08-28 | * PTR report * PV report | 20
10 | Final Review presentation | ENG + PJM | 2026-09-01 | 2 | 2026-09-11 | * All validation data | 20
11 | ECR ST40 (Order spec release in BOM) | ENG + DOC | 2026-09-14 | 2 | 2026-09-25 | * Final approval | 10
12 | SOP supplier | PPS + PUQ + SUP | 2026-09-28 | 1 | Onwards | * Customer approval | 5
13 | ECR close ST48 | ENG | 2026-09-29 | 2 | 2026-10-09 | * All documentation | 20

## ECR - Standard -5NC OVL
Project / ECR: 3E10134551: DV-E 5NC Overview List + Housing DRWs update
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR) | 04.08.2025 | 32 | 04.08.2025
3 | TR meeting | (ChR) | 04.12.2025 | 49 | 04.12.2025 | *-Drawings update *-OVL in update *- Drawings and OVL alignment and revision. *-Drawing and OVL in SAP in status 30. *-Drawing frozen (status 20 in SAP) *-Work On submission and approval *-ECR creation *-Alignment of activities to be done by MFE and PPS *-CTG evaluation. *-ECR application for TR & FR. *-ECR presentation.
4 | RACE submission for new PN if applies | (ENG)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS)
7 | First part of MP206 completion | (ChR)
8 | Counter measurement start date | (PUQ)
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR)
11 | PTR Date | (LOG/ChR)
12 | PV start date | (ChR/ENG)
13 | PV end date | (ChR/ENG)
14 | PTR and PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR) | 05.12.2025 | 49 | 05.12.2025 | *-Drawings update *-OVL in update *- Drawings and OVL alignment and revision. *-Drawing and OVL in SAP in status 30. *-Drawing frozen (status 20 in SAP) *-Work On submission and approval *-ECR creation *-Alignment of activities to be done by MFE and PPS *-CTG evaluation. *-ECR application for TR & FR. *-ECR presentation.
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Lcoal Change Co) | 30.06.2026 | 26 | 30.06.2026 | *-Approvals *-OVL in SAP in status 40 *-Drawing in TC in status 40
20 | Customer approval (full PSW) | (QMM)
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ) | 27.01.2026 | 26 | 30.06.2026 | *- PSW supplier
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG)
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT)
27 | ECR close ST48 | (CFT) | 10.07.2026 | 27 | 10.07.2026 | *-Revision of pending activities for ECR. *- Change representative and global change coordinator approval

## ECR - brp New Inlet design
Project / ECR: 3E10180125: Housing Order specification update - STLA T4 Evo DV-E 5.2 FL
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | CFT | 2026-05-14 |  | 2026-06-01 | Design confirmation Quotation BRP Approval | 60
2 | KO meeting | (ChR) | 2026-06-04 |  | 2026-06-18 | Steering committee approval | 15
3 | TR meeting | (ChR)
4 | RACE submission for new PN if applies | (ENG)
5 | Customer acceptance of the ECR | (PJM/Sales) | 2026-06-18 |  | 2026-06-25 |  | 5
6 | PTR parts available | (PPS) | 2026-10-05 |  | 2026-10-05 | Change at Eurocast | 5
7 | First part of MP206 completion | (ChR)
8 | Counter measurement start date | (PUQ)
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR)
11 | PTR Date | (LOG/ChR) | 2026-10-08 |  | 2026-10-08 | Housing available
12 | PV start date | (ChR/ENG) | 2026-10-14 |  | 2026-10-14 | Finish goods available
13 | PV end date | (ChR/ENG) | 2027-01-20 |  | 2027-01-20
14 | PTR and PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR) | 2027-01-28 |  | 2027-01-28 | PVPNR
18 | New PN release and available in SAP | (TEF6) | 2027-02-03 |  | 2027-02-03
19 | ECR ST40 | (ChR/Lcoal Change Co) | 2027-02-03 |  | 2027-02-03
20 | Customer approval (full PSW) | (QMM)
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG)
25 | Date of first batch arrival | (ChR) | 2027-02-10 |  | 2027-02-10
26 | SOP BOSCH | (CFT) | 2027-02-10 |  | 2027-02-10
27 | ECR close ST48 | (CFT) | 2027-02-10 |  | 2027-02-10