## New Program (hidden)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Project Award
2 | Project Kickoff
3 | Design phase
4 | Drawing release
5 | B- Design freeze
6 | Soft tooling
7 | B-samples production run
8 | B-samples
9 | DV
10 | DVP&R
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## ECR - Standard (1)
| Project / ECR: 3E10128035 | BASF material discontinuation (6002KP0673)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | 2025-01-09 |  | 2025-01-16
2 | KO meeting | (ChR) | 2025-04-25 |  | 2025-05-02
3 | TR meeting | (ChR) | 2025-04-28 |  | 2025-05-05
4 | RACE submission for new PN if applies | (ENG) | N/A |  | N/A
5 | Customer acceptance of the ECR | (PJM/Sales) | - |  | 2025-02-07
6 | PTR parts available | (PPS) | - |  | 2025-04-17
7 | First part of MP206 completion | (ChR) | - |  | -
8 | Counter measurement start date | (PUQ) | - |  | -
9 | Counter measurement end date | (PUQ) | - |  | -
10 | DL review and release if applies | (PUQ/ChR) | - |  | -
11 | PTR Date | (LOG/ChR) | N/A |  | N/A
12 | PV start date | (ChR/ENG) | N/A |  | N/A
13 | PV end date | (ChR/ENG) | - |  | 2025-09-26
14 | PTR and PV report | (MFE/ENG/QMM) | - |  | 2025-09-26
15 | Interim PSW | (ChR/PUQ) | N/A |  | N/A
16 | Customer validation completion | (ChR/ENG) | - |  | 2025-09-26
17 | Final Review presentation | (ChR) | 2026-02-13 |  | 2026-04-13
18 | New PN release and available in SAP | (TEF6) | - |  | 2024-12-13
19 | ECR ST40 | (ChR/Lcoal Change Co) | - |  | -
20 | Customer approval (full PSW) | (QMM) | 2026-03-27 |  | 2026-04-24
21 | PO Update | (Sales) | - |  | -
22 | Full PSW Supplier | (PUQ) | - |  | 2025-04-22
23 | Systematic release to supplier | (PPS/LOG) | - |  | -
24 | SOP supplier | (PPS/LOG) | 2026-05-14 |  | 2026-05-14
25 | Date of first batch arrival | (ChR) | 2026-05-22 |  | -
26 | SOP BOSCH | (CFT) | 2026-05-22 |  | -
27 | ECR close ST48 | (CFT) | 2026-05-29 |  | -

## ECR - Standard (2)
| Project / ECR: 3E10141881 | 6002KP0363 change to 158742000F
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR) | 2025-01-06 |  | 2025-01-17
3 | TR meeting | (ChR) | 2025-01-06 |  | 2025-01-17
4 | RACE submission for new PN if applies | (ENG) | 2025-01-20 |  | 2025-01-31
5 | Customer acceptance of the ECR | (PJM/Sales) | 2024-12-19 |  | 2024-12-19
6 | PTR parts available | (PPS) | N/A |  | N/A
7 | First part of MP206 completion | (ChR) | - |  | -
8 | Counter measurement start date | (PUQ) | N/A |  | N/A
9 | Counter measurement end date | (PUQ) | N/A |  | N/A
10 | DL review and release if applies | (PUQ/ChR) | N/A |  | N/A
11 | PTR Date | (LOG/ChR) | N/A |  | N/A
12 | PV start date | (ChR/ENG) | N/A |  | N/A
13 | PV end date | (ChR/ENG) | N/A |  | N/A
14 | PTR and PV report | (MFE/ENG/QMM) | N/A |  | N/A
15 | Interim PSW | (ChR/PUQ) | N/A |  | N/A
16 | Customer validation completion | (ChR/ENG) | N/A |  | N/A
17 | Final Review presentation | (ChR) | N/A |  | N/A
18 | New PN release and available in SAP | (TEF6) | 2025-02-10 |  | -
19 | ECR ST40 | (ChR/Lcoal Change Co) | 2025-02-04 |  | -
20 | Customer approval (full PSW) | (QMM) | 2025-04-14 |  | -
21 | PO Update | (Sales) | N/A |  | N/A
22 | Full PSW Supplier | (PUQ) | N/A |  | N/A
23 | Systematic release to supplier | (PPS/LOG) | N/A |  | N/A
24 | SOP supplier | (PPS/LOG) | N/A |  | N/A
25 | Date of first batch arrival | (ChR) | N/A |  | N/A
26 | SOP BOSCH | (CFT) | 2025-04-21 |  | -
27 | ECR close ST48 | (CFT) | 2025-04-21 |  | -

## ECR - Standard (3)
| Project / ECR: 3E10155743 | Cancellation of Part numbers (Ford)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | - |  | 2025-04-30
2 | KO meeting | (ChR) | - |  | 2025-05-14
3 | TR meeting | (ChR) | - |  | 2025-05-19
4 | RACE submission for new PN if applies | (ENG) | - |  | -
5 | Customer acceptance of the ECR | (PJM/Sales) | - |  | 2025-06-20
6 | PTR parts available | (PPS) | N/A |  | N/A
7 | First part of MP206 completion | (ChR) | N/A |  | N/A
8 | Counter measurement start date | (PUQ) | N/A |  | N/A
9 | Counter measurement end date | (PUQ) | N/A |  | N/A
10 | DL review and release if applies | (PUQ/ChR) | N/A |  | N/A
11 | PTR Date | (LOG/ChR) | N/A |  | N/A
12 | PV start date | (ChR/ENG) | N/A |  | N/A
13 | PV end date | (ChR/ENG) | N/A |  | N/A
14 | PTR and PV report | (MFE/ENG/QMM) | N/A |  | N/A
15 | Interim PSW | (ChR/PUQ) | N/A |  | N/A
16 | Customer validation completion | (ChR/ENG) | N/A |  | N/A
17 | Final Review presentation | (ChR) | - |  | 2025-10-24
18 | New PN release and available in SAP | (TEF6) | N/A |  | N/A
19 | ECR ST40 | (ChR/Lcoal Change Co) | - |  | -
20 | Customer approval (full PSW) | (QMM) | N/A |  | N/A
21 | PO Update | (Sales) | N/A |  | N/A
22 | Full PSW Supplier | (PUQ) | N/A |  | N/A
23 | Systematic release to supplier | (PPS/LOG) | N/A |  | N/A
24 | SOP supplier | (PPS/LOG) | N/A |  | N/A
25 | Date of first batch arrival | (ChR) | N/A |  | N/A
26 | SOP BOSCH | (CFT) | 2025-12-09 |  | -
27 | ECR close ST48 | (CFT) | - |  | -

## ECR - Standard (4)
| Project / ECR: 3E10175353 | BRP Sea-Doo FSMs -Updates per customer request (2nd label)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | 2026-02-03 |  | 2026-02-06
2 | KO meeting | (ChR) | 2026-02-02 |  | 2026-02-06
3 | TR meeting | (ChR) | 2026-02-09 |  | 2026-02-20
4 | RACE submission for new PN if applies | (ENG) | N/A |  | N/A
5 | Customer acceptance of the ECR | (PJM/Sales) | 2026-02-09 |  | 2026-02-13
6 | PTR parts available | (PPS) | N/A |  | N/A
7 | First part of MP206 completion | (ChR) | N/A |  | N/A
8 | Counter measurement start date | (PUQ) | N/A |  | N/A
9 | Counter measurement end date | (PUQ) | N/A |  | N/A
10 | DL review and release if applies | (PUQ/ChR) | N/A |  | N/A
11 | PTR Date | (LOG/ChR) | N/A |  | N/A
12 | PV start date | (ChR/ENG) | - |  | -
13 | PV end date | (ChR/ENG) | - |  | 2026-02-26
14 | PTR and PV report | (MFE/ENG/QMM) | - |  | 2026-03-27
15 | Interim PSW | (ChR/PUQ) | 2026-05-05 |  | -
16 | Customer validation completion | (ChR/ENG) | N/A |  | N/A
17 | Final Review presentation | (ChR) | 2026-04-20 |  | 2026-05-04
18 | New PN release and available in SAP | (TEF6) | N/A |  | N/A
19 | ECR ST40 | (ChR/Lcoal Change Co) | - |  | -
20 | Customer approval (full PSW) | (QMM) | 2026-06-11 |  | -
21 | PO Update | (Sales) | 2026-02-18 |  | 2026-04-17
22 | Full PSW Supplier | (PUQ) | - |  | -
23 | Systematic release to supplier | (PPS/LOG) | - |  | -
24 | SOP supplier | (PPS/LOG) | - |  | -
25 | Date of first batch arrival | (ChR) | - |  | -
26 | SOP BOSCH | (CFT) | 2026-06-18
27 | ECR close ST48 | (CFT) | - |  | -

## CO ECR (1)
| Task | Responsible | Start date | Leadtime | Finish date | Inputs | Workload (% hrs)
1 | KO meeting | (ChR) | 2026-04-29 |  | 2026-04-29
2 | TR meeting | (ChR) | 2026-05-11 |  | 2026-05-11
3 | Correction on SAP | (Doc. Department) | - |  | 2026-05-13
4 | ECR ST40 | (ChR/Local Change Co) | 2026-05-15 |  | -
5 | SOP BOSCH | (CFT) | 2026-03-06 |  | -
6 | ECR close ST48 | (Local Change Co) | 2026-05-29 |  | -