## New Program (hidden)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Project Award
2 | Project Kickoff
3 | Design phase
4 | Drawing release
5 | B- Design freeze
6 | Soft tooling
7 | B-samples production run
8 | B-samples
9 | DV
10 | DVP&R
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Flexline
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Project configuration | PJM | 2025-08-15 | 16 | 2025-12-04
2 | QG0 | PJM | 2026-02-06 | Milestone
3 | QG1 | PJM | 2026-04-16 | Milestone
4 | QG4 | PJM | 2027-04-08 | Milestone
5 | PIA-Workshop | PJM | 2025-10-06 | 2 | 2025-10-17
6 | PGL Assessment III | CFT | 2026-01-09 | Milestone
7 | Release BPS for MAR | BPS Leadplant | 2026-01-14 | 3 | 2026-02-06
8 | MAR approved | MFE SlpP | 2026-02-20 | Milestone
9 | Kick-off ECR-Team | QMM SlpP | 2026-02-02 | Milestone
10 | Customer negotiation | QMM SlpP | 2026-04-17 | 6 | 2026-05-30
11 | Team Review | CFT | 2026-05-07 | Milestone
12 | Design release | BMG | 2026-06-23 | Milestone
13 | Training @ BMG6 | BMG | 2026-11-09 | 5 | 2026-12-11
14 | Pre-acceptance @ supplier site | MFE SlpP | 2026-11-23 | 3 | 2026-12-11
15 | Dismantling | BMG | 2026-12-14 | 1 | 2026-12-22
16 | Transport untill arrival in SlpP | MFE SlpP | 2026-12-22 | 7 | 2027-02-11
17 | Area & infrastructure @ SlpP | MFE SlpP | 2026-06-23 | 26 | 2026-12-20
18 | SlpP area ready | MFE SlpP | 2026-12-20 | Milestone
19 | Commissioning | BMG | 2027-02-12 | 6 | 2027-03-26
20 | Final acceptance | MFE SlpP | 2027-03-26 | 2 | 2027-04-09
21 | Training @ SlpP | BMG | 2027-02-12 | 8 | 2027-04-09
22 | PTR / 0-series | MFE SlpP | 2027-04-09 | 2 | 2027-04-23
23 | P-FMEA | MFE SlpP | 2026-10-01 | Milestone
24 | CP | MFE SlpP | 2026-11-18 | Milestone
25 | MPF sheet | MFE SlpP | 2026-05-08 | Milestone
26 | Safe launch plan | QMM SlpP | 2026-05-22 | Milestone
27 | Parts tracking list | MFE SlpP | 2026-04-17 | Milestone
28 | Production release acc. MP-206.01 | MFE SlpP | 2027-04-09 | 3 | 2027-05-01
29 | int. SOP | MFE SlpP | 2027-05-02 | Milestone
30 | Measurement acc. Offer drawing | MFE SlpP | 2027-04-23 | 2 | 2027-05-07
31 | PPAP documentation | QMM SlpP | 2027-04-23 | 2 | 2027-05-07
32 | PV testing (more detailed description after commitment about strategy) | ENG | 2027-04-23 | 6 | 2027-06-04
33 | PPAP to customer | QMM SlpP | 2027-06-05 | Milestone
34 | Customer release phase | MFE SlpP | 2027-06-05 | 4 | 2027-07-03
35 | ext. SOP | MFE SlpP | 2027-07-03 | Milestone
36 | Safe launch incl. Ramp up support | QMM SlpP | 2027-07-03 | 4 | 2027-07-31

## 5NC Relocation
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Lines Comparison | CFT | 2025-07-01 | 13 | 2025-09-30
2 | Business continuity of SlpP line (Spare parts) | MFE SlpP | 2025-10-01 | 26 | 2026-03-31
3 | Kick off | PJM_relocation | 2026-04-01 | 13 | 2026-06-30
4 | TEF design and refurbishment | TEF NuP | 2026-07-01 | 52 | 2027-06-30
5 | Integration of SlpP types in Relocated Line | MFE SlpP / MFE NuP | 2026-04-01 | 26 | 2026-09-30
6 | Prepare layout | MFE SlpP | 2026-10-01 | 26 | 2027-04-01
7 | Stock building at Origin | MFE NuP | 2027-07-01 | 13 | 2027-09-30
8 | Shipping to SlpP | MFE NuP | 2027-10-01 | 13 | 2027-12-31
9 | Re-assembly | MFE SlpP / MFE NuP | 2028-01-01 | 13 | 2028-03-31
10 | Internal Release | MFE SlpP | 2028-04-01 | 26 | 2028-09-30
11 | Customer Release | MFE SlpP / QMM SlpP / QMM NuP | 2028-07-01 | 26 | 2028-12-31
Formulas:
Leadtime (CW) = ROUND(DAYS([Finish date],[Start date])/7,0)

## Subassembly Consolidation
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Area ready to receive the stations | BPS | 2026-01-16 | Milestone | 2026-01-16
2 | Kick off | BPS | 2026-01-19 | Milestone | 2026-01-19
3 | Move Molding Shaft | BPS | 2026-07-10 | Milestone | 2026-07-10
4 | Install Coupling Unit (ST37) New | BPS | 2026-01-26 | Milestone | 2026-01-26
5 | Move Coupling Unit (ST37) Current | BPS | 2026-08-17 | Milestone | 2026-08-17
6 | Move Cover Ramming (St65) | BPS | 2026-09-30 | Milestone | 2026-09-30
7 | Move Shaft C-Clip | BPS | 2026-11-20 | Milestone | 2026-11-20
8 | Move Manual Coupling Unit | BPS | 2026-11-20 | Milestone | 2026-11-20
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
Formulas:
Leadtime (CW) = IF(ROUND(DAYS([Finish date],[Start date])/7,0)=0,"Milestone",ROUND(DAYS([Finish date],[Start date])/7,0))

## ECR - Standard (hidden)
Project / ECR:
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR)
4 | RACE submission for new PN if applies | (ENG)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS)
7 | First part of MP206 completion | (ChR)
8 | Counter measurement start date | (PUQ)
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR)
11 | PTR Date | (LOG/ChR)
12 | PV start date | (ChR/ENG)
13 | PV end date | (ChR/ENG)
14 | PTR and PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR)
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Lcoal Change Co)
20 | Customer approval (full PSW) | (QMM)
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG)
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT)
27 | ECR close ST48 | (CFT)

## ECR Manager Decision (hidden)
| Task | Responsible | Start date | Leadtime | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR)
4 | PTR parts available | (PPS)
5 | First part of MP206 completion | (ChR)
6 | Counter measurement start date | (PUQ)
7 | Counter measurement end date | (PUQ)
8 | DL review and release if applies | (PUQ/ChR)
9 | PTR Date | (LOG/ChR)
10 | PTR and PV report | (ChR/ENG)
11 | Interim PSW | (ChR/PUQ)
12 | Final Review presentation | (ChR)
13 | ECR ST40 | (ChR/Lcoal Change Co)
14 | Full PSW Supplier | (PUQ)
15 | Systematic release to supplier | (PPS/LOG)
16 | SOP supplier | (PPS/LOG)
17 | Date of first batch arrival | (ChR)
18 | SOP BOSCH | (CFT)
19 | ECR close ST48 | (CFT)

## CO ECR (hidden)
| Task | Responsible | Start date | Leadtime | Finish date | Inputs | Workload (% hrs)
1 | KO meeting | (ChR)
2 | TR meeting | (ChR)
3 | Correction on SAP | (Doc. Department)
4 | ECR ST40 | (ChR/Local Change Co)
5 | SOP BOSCH | (CFT)
6 | ECR close ST48 | (Local Change Co)

## Global ECR (hidden)
| Task | Responsible | Start date | Leadtime | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR)
4 | RACE submission for new PN if applies | (ENG)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS)
7 | First part of MP206 completion | (ChR)
8 | Counter measurement start date | (PUQ)
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR)
11 | PTR Date | (LOG/ChR)
12 | PV start date | (ChR/ENG)
13 | PV end date | (ChR/ENG)
14 | PTR and PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR)
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Local Change Co)
20 | Customer approval (full PSW) | (QMM)
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG)
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT)
27 | ECR close ST48 | (CFT)