## New Program (hidden)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Project Award
2 | Project Kickoff
3 | Design phase
4 | Drawing release
5 | B- Design freeze
6 | Soft tooling
7 | B-samples production run
8 | B-samples
9 | DV
10 | DVP&R
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## ECR - 3E10171456 (T4EVO Cap)
| Project / ECR: | 3E10171456 T4EVO Cap
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | [5 empty] | 3E10153553 (Ford)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR) | CW16 | 1 | CW17
4 | RACE submission for new PN if applies | (ENG) | [5 empty] | 3E10153559 (VW)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS) | CW29 | 2 | CW31
7 | First part of MP206 completion | (ChR)
8 | Counter measurement | (PUQ) | - | - | -
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR) | - | - | -
11 | PTR Date | (LOG/ChR) | CW32 | 1 | CW33
12 | PV start date | (ChR/ENG) | - | - | -
13 | PV end date | (ChR/ENG)
14 | PTR report | (MFE/ENG/QMM) | CW32 | 1 | CW33
14.1 | PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR) | CW34 | 1 | CW35
18 | New PN release and available in SAP | (TEF6) | CW34 | 1 | CW35
19 | ECR ST40 | (ChR/Lcoal Change Co) | CW34 | 1 | CW35
20 | Customer approval (full PSW) | (QMM) | CW36 | 3 | CW39
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ) | CW40 | 1 | CW41
23 | Systematic release to supplier | (PPS/LOG) | CW41 | 2 | CW43
24 | SOP supplier | (PPS/LOG) | CW41 | 2 | CW43
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT) | CW44 | 0 | CW44
27 | ECR close ST48 | (CFT)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)

## 3E10148721 T6 Tube (Scherdel)
| Project / ECR: | 3E10148721 T6 Tube (Scherdel)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR) | 2025 | - | 2025
4 | RACE submission for new PN if applies | (ENG)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS) | CW26 | 1 | CW27
7 | First part of MP206 completion | (ChR)
8 | Counter measurement | (PUQ) | CW28 | 1 | CW30
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR) | CW31 | 1 | CW32
11 | PTR Date | (LOG/ChR) | CW33 | 2 | CW35
12 | PV start date | (ChR/ENG) | CW38 | 11 | CW49
13 | PV end date | (ChR/ENG)
14 | PTR report | (MFE/ENG/QMM) | CW33 | 2 | CW35
14.1 | PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR) | CW50 | 1 | CW51
18 | New PN release and available in SAP | (TEF6) | CW50 | 1 | CW51
19 | ECR ST40 | (ChR/Lcoal Change Co) | CW50 | 1 | CW51
20 | Customer approval (full PSW) | (QMM) | CW50 | 2 | CW52
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ) | CW50 | 3 | CW01 2027
23 | Systematic release to supplier | (PPS/LOG) | CW02 | 3 | CW05
24 | SOP supplier | (PPS/LOG) | CW02 | 3 | CW05
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT) | CW06 | - | CW06
27 | ECR close ST48 | (CFT)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)

## ECR - Standard 3E10153365 STLA
| Project / ECR: | 3E10153365 (STLA)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | [5 empty] | 3E10153553 (Ford)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR) | W15 2026 | 1 | W15 2026
4 | RACE submission for new PN if applies | (ENG) | [5 empty] | 3E10153559 (VW)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS) | W39 2026 | 3 | W42 2026
7 | First part of MP206 completion | (ChR)
8 | Counter measurement | (PUQ) | W05 2026 | 10 | W15 2026
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR) | NA | NA | NA
11 | PTR Date | (LOG/ChR) | W07 2026 | 1 | W07 2026
12 | PV start date | (ChR/ENG) | W05 2026 | 9 | W14 2026
13 | PV end date | (ChR/ENG)
14 | PTR report | (MFE/ENG/QMM)
14.1 | PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR)
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Lcoal Change Co)
20 | Customer approval (full PSW) | (QMM) | W07 2026 | 31 | W38 2026
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG) | W31 2026 | 1 | W31 2026
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT) | W43 2026 | 1 | W43 2026
27 | ECR close ST48 | (CFT)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)

## ECR - Standard 3E10153559 (VW)
| Project / ECR: | 3E10153559 (VW)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | [5 empty] | 3E10153553 (Ford)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR) | W15 2026 | 1 | W15 2026
4 | RACE submission for new PN if applies | (ENG) | [5 empty] | 3E10153559 (VW)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS) | W39 2026 | 3 | W42 2026
7 | First part of MP206 completion | (ChR)
8 | Counter measurement | (PUQ) | W05 2026 | 10 | W15 2026
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR) | NA | NA | NA
11 | PTR Date | (LOG/ChR)
12 | PV start date | (ChR/ENG)
13 | PV end date | (ChR/ENG)
14 | PTR report | (MFE/ENG/QMM)
14.1 | PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR)
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Lcoal Change Co)
20 | Customer approval (full PSW) | (QMM)
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG)
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT)
27 | ECR close ST48 | (CFT)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)

## ECR - 3E10153553 (Ford))
| Project / ECR: | 3E10153553 (Ford)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | [6 empty] | 3E10153553 (Ford)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR) | W15 2026 | 1 | W15 2026
4 | RACE submission for new PN if applies | (ENG) | [6 empty] | 3E10153559 (VW)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS) | W39 2026 | 3 | W42 2026
7 | First part of MP206 completion | (ChR)
8 | Counter measurement | (PUQ) | W05 2026 | 10 | W15 2026
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR) | NA | NA | NA
11 | PTR Date | (LOG/ChR)
12 | PV start date | (ChR/ENG)
13 | PV end date | (ChR/ENG)
14 | PTR report | (MFE/ENG/QMM)
14.1 | PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR)
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Lcoal Change Co)
20 | Customer approval (full PSW) | (QMM) | [5 empty] | Not defined yet customer approval date
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG) | [5 empty] | Not defined yet customer approval date
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT) | [5 empty] | Not defined yet customer approval date
27 | ECR close ST48 | (CFT)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)

## ECR - 3E10153663 (Rotax 46mm)
| Project / ECR: | 3E10153663 (Rotax 46mm)
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) | [5 empty] | 3E10153553 (Ford)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR) | W15 2026 | 1 | W15 2026
4 | RACE submission for new PN if applies | (ENG) | [5 empty] | 3E10153559 (VW)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS) | W39 2026 | 3 | W42 2026
7 | First part of MP206 completion | (ChR)
8 | Counter measurement | (PUQ) | W05 2026 | 10 | W15 2026
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR) | NA | NA | NA
11 | PTR Date | (LOG/ChR)
12 | PV start date | (ChR/ENG)
13 | PV end date | (ChR/ENG)
14 | PTR report | (MFE/ENG/QMM)
14.1 | PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR)
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Lcoal Change Co)
20 | Customer approval (full PSW) | (QMM) | W07 2026 | 37 | W44 2026
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG) | W33 2026 | 1 | W33 2026
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT) | W45 2026 | 1 | W45 2026
27 | ECR close ST48 | (CFT)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)
[6 empty] | Inputs | Workload (% hrs)