## New Program - DVE BRP 54mm NC
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Project Award | Aq. Mngr. | - |  | -
2 | Project Kickoff | PjM | 2025-04-07 |  | 2025-04-07
3 | Design phase | ENG | 2025-06-09
4 | B- Design freeze | ENG | 2025-10-02
5 | QGC0 | PjM | 2025-10-02 |  | 2025-10-02
6 | Soft tooling | ENG | -
7 | B-samples production run | ENG | -
8 | B-samples | ENG | -
9 | DV | ENG | -
10 | DVP&R | ENG | -
11 | C-component design freeze | ENG | 2025-11-14 |  | 2025-11-14
12 | Drawing release | ENG | 2026-04-04 |  | 2026-04-04
13 | Sourcing | PPS | 2025-11-03 |  | 2025-11-28
14 | Line Retrofit | MSE | 2025-12-15 |  | 2027-02-26
15 | PFMEA | MSE | 2026-04-20 |  | 2026-08-19
16 | Line Release | MSE | 2026-04-27 |  | 2027-08-31
17 | 10 Digits MM | PjM | 2026-03-13 |  | 2026-03-13
18 | DFMEA | ENG
19 | C-component release | PUQ | 2026-11-12 |  | 2026-11-12
20 | IMDS | ENG
21 | MDM | PUQ/QMM
22 | PTR | QMM | 2026-08-14 |  | 2026-08-14
23 | PVP | QMM | 2026-08-17 |  | 2027-01-29
24 | PVP&R | QMM | 2027-02-01 |  | 2027-02-19
25 | 13 Digits release | PjM | 2026-10-23 |  | 2026-11-13
26 | Zero series | MSE / QMM
27 | PPAP submission | QMM | 2027-03-05 |  | 2027-03-05
28 | PPAP approval | QMM | 2027-05-18 |  | 2027-05-18
29 | QGC4 | PjM | 2027-02-15 |  | 2027-02-15
30 | SOP | MSE/QMM | 2027-05-18 |  | 2027-05-18

## ECR Standard- EKP 13 01G
Project / ECR: | ECR 3E10144732 – Pump para 2154 -> (0580.454.00U → 0580.454.01G)
Column1 | Task | Responsible | Start date | Leadtime (Days) | Leadtime (wks) | Finish date | Inputs | Workload (% hrs) | % COMPLETE
1 | Business case available | (ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | * Supplier feasibility *Task force activities, customer meetings * Quotation for the change from supplier * Updated drawing | 45 | 100%
2 | KO meeting | (ChR) | 2025-01-01 | 0 | 0 | 2025-01-01 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25 | 100%
3 | TR meeting | (ChR) | 2025-01-01 | 0 | 0 | 2025-01-01 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25 | 100%
4 | RACE submission for new PN if applies | (ENG) | NA | NA | NA | NA | NA | NA | NA
5 | Customer acceptance of the ECR | (PJM/Sales) | 2025-02-01 | 7 | 1 | 2025-02-08 | * Customer technical meetings * Design definition | 15 | 100%
6 | PTR parts available | (PPS) | 2025-05-20 | 6 | 0.85714 | 2025-05-26 | * Updated Drawing * Feasilibity confirmation * Purchasing Order | 20 | 100%
7 | First part of MP206 completion | (ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | * PTR parts * Manufacturing setup | 30 | 100%
8 | Counter measurement start date | (PUQ) | 2025-05-26 | 0 | 0 | 2025-05-26 | NA | NA | 100%
9 | Counter measurement end date | (PUQ) | 2025-05-26 | 0 | 0 | 2025-05-26 | * Counter measurement data * Analysis results | 20 | 100%
10 | DL review and release if applies | (PUQ/ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | * QMM Test results * PTR results (EoL test, airflow) * DL with proposed deviations | 15 | 100%
11 | Supplier Full Release | (PUQ/ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | *PSW Full Approval | 15 | 100%
11 | PTR Date | (LOG/ChR) | 2026-06-06 | 0 | 0 | 2026-06-06 | * Pieces available with the machined LMS at 15.3° | 10 | 100%
12 | PV start date | (ChR/ENG) | 2025-12-12 | 0 | 0 | 2025-12-12 | * PTR approval * Pieces available within specification | 15 | 100%
13 | PV end date | (ChR/ENG) | 2026-04-14 | 0 | 0 | 2026-04-14 | * Production validation tests | 25 | 100%
14 | PTR and PV report | (MFE/ENG/QMM) | 2026-04-14 | 0 | 0 | 2026-04-14 | * All test data * Validation results * Teardown Analysis | 20 | 100%
15 | Interim PSW | (ChR/PUQ) | NA | NA | NA | NA | * PTR report * PV report | 15 | NA
16 | Customer validation completion | (ChR/ENG) | 2026-04-14 | 0 | 0 | 2026-04-14 | * Interim PSW * Customer testing | 20 | 100%
17 | Final Review presentation | (ChR) | 2026-04-14 | 0 | 0 | 2026-04-14 | * All validation data | 25 | 100%
18 | New PN release and available in SAP | (TEF6) | 2026-02-20 | 0 | 0 | 2026-02-20 | * Final approval | 10 | 100%
19 | ECR ST40 | (ChR/Lcoal Change Co) | 2026-04-21 | 0 | 0 | 2026-04-21 | * PN release confirmation | 5 | 100%
20 | 0/Series | (MSE) | 2026-06-01 | 0 | 0 | 2026-06-01 | *TLP Procedure |  | 0%
21 | PPAP Submission *from TLP to Customer | (QMM) | 2026-06-17 | 27 | 3.8571 | 2026-07-14 | *Final PPAP submission |  | 0%
22 | PPAP Approval *from Customer to TLP | (QMM) | 2026-07-15 | 27 | 3.8571 | 2026-08-11 | * Complete documentation | 15 | 0%
23 | PO Update | (Sales) | 2026-05-21 | 8 | 1.1429 | 2026-05-29 | * Customer approval | 5 | 0%
24 | Full PSW Supplier | (PUQ) | NA | NA | NA | NA | * All documentation | 20 | 0%
25 | Systematic release to supplier | (PPS/LOG) | 2026-08-11 | 11 | 1.5714 | 2026-08-22 | * Full PSW complete | 10 | 0%
26 | SOP supplier | (PPS/LOG) | 2027-01-01 | 0 | 0 | 2027-01-01 | * Production readiness | 25 | 0%
27 | Date of first batch arrival | (ChR) |  | 0 | 0 |  | * SOP confirmation | 5 | 0%
28 | SOP BOSCH | (CFT) | 2026-09-04 | 0 | 0 | 2026-09-04 | * First batch received | 15 | 0%
29 | ECR close ST48 | (CFT) |  | 0 | 0 |  | * SOP complete | 5 | 0%

## ECR Standard - EKP 13 01D
Project / ECR: | RACE FXRC126580 – Pump para 1895 RACE FXRC126584 – Pump para 1896
Column1 | Task | Responsible | Start date | Leadtime (Days) | Leadtime (wks) | Finish date | Inputs | Workload (% hrs) | % COMPLETE
1 | Business case available | (ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | * Supplier feasibility *Task force activities, customer meetings * Quotation for the change from supplier * Updated drawing | 45 | 100%
2 | KO meeting | (ChR) | 2025-01-01 | 0 | 0 | 2025-01-01 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25 | 100%
3 | TR meeting | (ChR) | 2025-01-01 | 0 | 0 | 2025-01-01 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25 | 100%
4 | RACE submission for new PN if applies | (ENG) | 2026-05-04 | 14 | 2 | 2026-05-18 | NA | NA | NA
5 | Customer acceptance of the ECR | (PJM/Sales) | 2025-02-01 | 7 | 1 | 2025-02-08 | * Customer technical meetings * Design definition | 15 | 100%
6 | PTR parts available | (PPS) | 2025-05-20 | 6 | 0.85714 | 2025-05-26 | * Updated Drawing * Feasilibity confirmation * Purchasing Order | 20 | 100%
7 | First part of MP206 completion | (ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | * PTR parts * Manufacturing setup | 30 | 100%
8 | Counter measurement start date | (PUQ) | 2025-05-26 | 0 | 0 | 2025-05-26 | NA | NA | 100%
9 | Counter measurement end date | (PUQ) | 2025-05-26 | 0 | 0 | 2025-05-26 | * Counter measurement data * Analysis results | 20 | 100%
10 | DL review and release if applies | (PUQ/ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | * QMM Test results * PTR results (EoL test, airflow) * DL with proposed deviations | 15 | 100%
11 | Supplier Full Release | (PUQ/ChR) | 2025-05-26 | 0 | 0 | 2025-05-26 | *PSW Full Approval | 15 | 100%
11 | PTR Date | (LOG/ChR) | 2026-06-06 | 0 | 0 | 2026-06-06 | * Pieces available with the machined LMS at 15.3° | 10 | 100%
12 | PV start date | (ChR/ENG) | 2025-12-12 | 0 | 0 | 2025-12-12 | * PTR approval * Pieces available within specification | 15 | 100%
13 | PV end date | (ChR/ENG) | 2026-04-14 | 0 | 0 | 2026-04-14 | * Production validation tests | 25 | 100%
14 | PTR and PV report | (MFE/ENG/QMM) | 2026-04-14 | 0 | 0 | 2026-04-14 | * All test data * Validation results * Teardown Analysis | 20 | 100%
15 | Interim PSW | (ChR/PUQ) | NA | NA | NA | NA | * PTR report * PV report | 15 | NA
16 | Customer validation completion | (ChR/ENG) | 2026-04-14 | 0 | 0 | 2026-04-14 | * Interim PSW * Customer testing | 20 | 100%
17 | Final Review presentation | (ChR) | 2026-04-14 | 0 | 0 | 2026-04-14 | * All validation data | 25 | 100%
18 | New PN release and available in SAP | (TEF6) | 2026-02-20 | 0 | 0 | 2026-02-20 | * Final approval | 10 | 100%
19 | ECR ST40 | (ChR/Lcoal Change Co) | 2026-04-21 | 0 | 0 | 2026-04-21 | * PN release confirmation | 5 | 100%
20 | 0/Series | (MSE) | 2026-06-23 | 6 | 0.85714 | 2026-06-29 | *TLP Procedure |  | 0%
21 | PPAP Submission *from TLP to Customer | (QMM) | 2026-07-14 | 27 | 3.8571 | 2026-08-10 | *Final PPAP submission |  | 0%
22 | PPAP Approval *from Customer to TLP | (QMM) | 2026-08-11 | 27 | 3.8571 | 2026-09-07 | * Complete documentation | 15 | 0%
23 | PO Update | (Sales) | 2026-05-21 | 8 | 1.1429 | 2026-05-29 | * Customer approval | 5 | 0%
24 | Full PSW Supplier | (PUQ) | NA | NA | NA | NA | * All documentation | 20 | 0%
25 | Systematic release to supplier | (PPS/LOG) | 2026-08-11 | 11 | 1.5714 | 2026-08-22 | * Full PSW complete | 10 | 0%
26 | SOP supplier | (PPS/LOG) |  | 0 | 0 |  | * Production readiness | 25 | 0%
27 | Date of first batch arrival | (ChR) |  | 0 | 0 |  | * SOP confirmation | 5 | 0%
28 | SOP BOSCH | (CFT) | 2026-06-29 | 9 | 1.2857 | 2026-07-08 | * First batch received | 15 | 0%
29 | ECR close ST48 | (CFT) |  | 0 | 0 |  | * SOP complete | 5 | 0%

## ECR Standard - Nissan
Project / ECR: | 3E10165605 – Nissan & STLA Reservoir – 2026
Column1 | Task | Responsible | Start date | Leadtime (Days) | Leadtime (wks) | Finish date | Inputs | Workload (% hrs) | % COMPLETE
1 | Business case available | (ChR) | 2025-10-13 | 0 | 0 | 2025-10-13 | * Supplier feasibility *Task force activities, customer meetings * Quotation for the change from supplier * Updated drawing | 45 | 100%
2 | KO meeting | (ChR) | 2026-01-22 | 7 | 1 | 2026-01-29 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25 | 100%
3 | TR meeting | (ChR) | 2026-02-09 | 4 | 0.57143 | 2026-02-13 | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25 | 100%
4 | RACE submission for new PN if applies | (ENG) | NA | NA | NA | NA | NA | NA | NA
5 | Customer acceptance of the ECR | (PJM/Sales) | 2026-02-13 | 14 | 2 | 2026-03-27 | * Customer technical meetings * Design definition | 15 | 100%
6 | PTR parts available | (PPS) | 2026-04-20 | 18 | 2.5714 | 2026-05-08 | * Updated Drawing * Feasilibity confirmation * Purchasing Order | 20 | 100%
7 | First part of MP206 completion | (ChR) |  | 0 | 0 |  | * PTR parts * Manufacturing setup | 30 | 0%
8 | Counter measurement start date | (PUQ) | 2026-05-22 | 0 | 0 | 2026-05-22 | NA | NA | 0%
9 | Counter measurement end date | (PUQ) | 2026-05-29 | 0 | 0 | 2026-05-29 | * Counter measurement data * Analysis results | 20 | 0%
10 | DL review and release if applies | (PUQ/ChR) | 2026-05-29 | 7 | 1 | 2026-06-05 | * QMM Test results * PTR results (EoL test, airflow) * DL with proposed deviations | 15 | 0%
11 | Supplier Full Release | (PUQ/ChR) | 2026-06-05 | 7 | 1 | 2026-06-12 | *PSW Full Approval | 15 | 0%
11 | PTR Date | (LOG/ChR) | 2026-06-01 | 4 | 0.57143 | 2026-06-05 | * Pieces available with the machined LMS at 15.3° | 10 | 50%
12 | PV start date | (ChR/ENG) | 2026-06-22 | 0 | 0 | 2026-06-22 | * PTR approval * Pieces available within specification | 15 | 0%
13 | PV end date | (ChR/ENG) | 2026-07-17 | 0 | 0 | 2026-07-17 | * Production validation tests | 25 | 0%
14 | PTR and PV report | (MFE/ENG/QMM) | 2026-08-14 | 0 | 0 | 2026-08-14 | * All test data * Validation results * Teardown Analysis | 20 | 0%
15 | Interim PSW | (ChR/PUQ) | NA | NA | NA | NA | * PTR report * PV report | 15 | NA
16 | Customer validation completion | (ChR/ENG) | 2026-08-14 | 0 | 0 | 2026-08-14 | * Interim PSW * Customer testing | 20 | 0%
17 | Final Review presentation | (ChR) | 2026-08-14 | 7 | 1 | 2026-08-21 | * All validation data | 25 | 0%
18 | New PN release and available in SAP | (TEF6) | 2026-08-14 | 0 | 0 | 2026-08-14 | * Final approval | 10 | 0%
19 | ECR ST40 | (ChR/Lcoal Change Co) | 2026-07-24 | 0 | 0 | 2026-07-24 | * PN release confirmation | 5 | 0%
20 | 0/Series | (MSE) | 2026-07-27 | 4 | 0.57143 | 2026-07-31 | *TLP Procedure |  | 0%
21 | PPAP Submission *from TLP to Customer | (QMM) | 2026-08-17 | 25 | 3.5714 | 2026-09-11 | *Final PPAP submission |  | 0%
22 | PPAP Approval *from Customer to TLP | (QMM) | 2026-09-14 | 25 | 3.5714 | 2026-10-09 | * Complete documentation | 15 | 0%
23 | PO Update | (Sales) | 2026-10-09 | 0 | 0 | 2026-10-09 | * Customer approval | 5 | 0%
24 | Full PSW Supplier | (PUQ) | NA | NA | NA | NA | * All documentation | 20 | 0%
25 | Systematic release to supplier | (PPS/LOG) | 2026-10-09 | 0 | 0 | 2026-10-09 | * Full PSW complete | 10 | 0%
26 | SOP supplier | (PPS/LOG) | 2026-07-02 | 6 | 0.85714 | 2026-07-08 | * Production readiness | 25 | 0%
27 | Date of first batch arrival | (ChR) | 2026-12-01 | 0 | 0 | 2026-12-01 | * SOP confirmation | 5 | 0%
28 | SOP BOSCH | (CFT) | 2026-12-01 | 0 | 0 | 2026-12-01 | * First batch received | 15 | 0%
29 | ECR close ST48 | (CFT) |  | 0 | 0 |  | * SOP complete | 5 | 0%