## New Program
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Project Award
2 | Project Kickoff
3 | Design phase
4 | Drawing release
5 | B- Design freeze
6 | Soft tooling
7 | B-samples production run
8 | B-samples
9 | DV
10 | DVP&R
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## CIP
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | New Set up standard alignment
2 | Technical Evaluation of new standard |  |  |  |  | * Edge break measurements
3 | Change of documentation (set up release format) |  |  |  |  | * ENG Lead development reviews * Data on how is performed in SlpP, machinning plate line
4 | New Standard implementation |  |  |  |  | * Business case for supplier * Business case for implementation inhouse
5 | Evaluation / Feedback of new standard |  |  |  |  | *New standard implemented
6 | Change over concept training
7 | Lessons Learned sharing

## ECR - Standard
| Project / ECR: | 40 / 60 MM development
| Task | Responsible | Start date | Leadtime (CW) | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR) |  |  |  | * Supplier feasibility *Task force activities, customer meetings * Quotation for the change from supplier * Updated drawing | 45
2 | KO meeting | (ChR) |  |  |  | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25
3 | TR meeting | (ChR) |  |  |  | *ECR * Updated drawing * Customer presentation * CTG Checklist | 25
4 | RACE submission for new PN if applies | (ENG) |  |  |  | NA | NA
5 | Customer acceptance of the ECR | (PJM/Sales) |  |  |  | * Customer technical meetings * Design definition | 15
6 | PTR parts available | (PPS) |  |  |  | * Updated Drawing * Feasilibity confirmation * Purchasing Order | 20
7 | First part of MP206 completion | (ChR) |  |  |  | * PTR parts * Manufacturing setup | 30
8 | Counter measurement start date | (PUQ) |  |  |  | NA | NA
9 | Counter measurement end date | (PUQ) |  |  |  | * Counter measurement data * Analysis results | 20
10 | DL review and release if applies | (PUQ/ChR) |  |  |  | * QMM Test results * PTR results (EoL test, airflow) * DL with proposed deviations | 15
11 | PTR Date | (LOG/ChR) |  |  |  | * Pieces available with the machined LMS at 15.3° | 10
12 | PV start date | (ChR/ENG) |  |  |  | * PTR approval * Pieces available within specification | 15
13 | PV end date | (ChR/ENG) |  |  |  | * Production validation tests | 25
14 | PTR and PV report | (MFE/ENG/QMM) |  |  |  | * All test data * Validation results * Teardown Analysis | 20
15 | Interim PSW | (ChR/PUQ) |  |  |  | * PTR report * PV report | 15
16 | Customer validation completion | (ChR/ENG) |  |  |  | * Interim PSW * Customer testing | 20
17 | Final Review presentation | (ChR) |  |  |  | * All validation data | 25
18 | New PN release and available in SAP | (TEF6) |  |  |  | * Final approval | 10
19 | ECR ST40 | (ChR/Lcoal Change Co) |  |  |  | * PN release confirmation | 5
20 | Customer approval (full PSW) | (QMM) |  |  |  | * Complete documentation | 15
21 | PO Update | (Sales) |  |  |  | * Customer approval | 5
22 | Full PSW Supplier | (PUQ) |  |  |  | * All documentation | 20
23 | Systematic release to supplier | (PPS/LOG) |  |  |  | * Full PSW complete | 10
24 | SOP supplier | (PPS/LOG) |  |  |  | * Production readiness | 25
25 | Date of first batch arrival | (ChR) |  |  |  | * SOP confirmation | 5
26 | SOP BOSCH | (CFT) |  |  |  | * First batch received | 15
27 | ECR close ST48 | (CFT) |  |  |  | * SOP complete | 5

## ECR Manager Decision
| Task | Responsible | Start date | Leadtime | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR)
4 | PTR parts available | (PPS)
5 | First part of MP206 completion | (ChR)
6 | Counter measurement start date | (PUQ)
7 | Counter measurement end date | (PUQ)
8 | DL review and release if applies | (PUQ/ChR)
9 | PTR Date | (LOG/ChR)
10 | PTR and PV report | (ChR/ENG)
11 | Interim PSW | (ChR/PUQ)
12 | Final Review presentation | (ChR)
13 | ECR ST40 | (ChR/Lcoal Change Co)
14 | Full PSW Supplier | (PUQ)
15 | Systematic release to supplier | (PPS/LOG)
16 | SOP supplier | (PPS/LOG)
17 | Date of first batch arrival | (ChR)
18 | SOP BOSCH | (CFT)
19 | ECR close ST48 | (CFT)

## CO ECR
| Task | Responsible | Start date | Leadtime | Finish date | Inputs | Workload (% hrs)
1 | KO meeting | (ChR)
2 | TR meeting | (ChR)
3 | Correction on SAP | (Doc. Department)
4 | ECR ST40 | (ChR/Local Change Co)
5 | SOP BOSCH | (CFT)
6 | ECR close ST48 | (Local Change Co)

## Global ECR
| Task | Responsible | Start date | Leadtime | Finish date | Inputs | Workload (% hrs)
1 | Business case available | (ChR)
2 | KO meeting | (ChR)
3 | TR meeting | (ChR)
4 | RACE submission for new PN if applies | (ENG)
5 | Customer acceptance of the ECR | (PJM/Sales)
6 | PTR parts available | (PPS)
7 | First part of MP206 completion | (ChR)
8 | Counter measurement start date | (PUQ)
9 | Counter measurement end date | (PUQ)
10 | DL review and release if applies | (PUQ/ChR)
11 | PTR Date | (LOG/ChR)
12 | PV start date | (ChR/ENG)
13 | PV end date | (ChR/ENG)
14 | PTR and PV report | (MFE/ENG/QMM)
15 | Interim PSW | (ChR/PUQ)
16 | Customer validation completion | (ChR/ENG)
17 | Final Review presentation | (ChR)
18 | New PN release and available in SAP | (TEF6)
19 | ECR ST40 | (ChR/Local Change Co)
20 | Customer approval (full PSW) | (QMM)
21 | PO Update | (Sales)
22 | Full PSW Supplier | (PUQ)
23 | Systematic release to supplier | (PPS/LOG)
24 | SOP supplier | (PPS/LOG)
25 | Date of first batch arrival | (ChR)
26 | SOP BOSCH | (CFT)
27 | ECR close ST48 | (CFT)